## home
KSCC BIWEEKLY PROGRESS REPORT 30/09/2020
Sl No: | SPV | Project Code | Project Name | Sub-Project Name | Package Name/Package code | District | Accepted Tender Amount (Cr) | Name of Contractor | Duration of work (Months) | Date of Commencement | Due date of completion | Extended date of completion | Current Progress in Detail | Physical Progress (%) |  |  | Financial Progress (in Cr) | Percentage of Bill Amount Sanctioned (%) | PMU Head Name & Contact No: | Project-in-charge Name & Contact No: | Last Bill details | Tendative Date for the next bill Due
[14 empty] | Planned | Achieved | Compliance
1 | KSCC | HOM001-01 | Home Department - Judiciary - Construction of Court Complex at Thalassery under KIIFB |  | HOM001-01-01 | Kannur | 37.22 | Nirman Constructions Malappuram | 24months | 07.07.2020 | 06.07.2020 | _ | Preparatory work (shifting of Court,Temporary arrangements for office ,parking area arrangements etc)as requested by Judge in progress. Treefelling in site compound completed. | [5 empty] | Rema.P.K(GM) 9497186255 | Sri. Roy. P.S,RM, Kannur,9447716468
2 | KSCC | HOM001-02 | Construction of Court Complex at Koothuparamba in Kannur District | _ | _ | Kannur | Project Appraisal under KIIFB in progress
3 | KSCC | HOM001-03 | Construction of Court Complex at Ranni in Pathanamthitta District under KIIFB | _ | _ | Pathanamthitta | Project Appraisal under KIIFB in progress
4 | KSCC | HOM001-04 | Construction of Court Complex at Palakkad under KIIFB | _ | _ | Palakkad | Project Appraisal under KIIFB in progress
5 | KSCC | HOM001-05 | Construction of Court Complex at Nedumkandom in Idukki District | _ | _ | Idukki | Project Appraisal under KIIFB in progress
6 | KSCC | HOM001-06 | Home Department -Judiciary -Construction of Court Complex at Peerumedu in Idukki District under KIIFB | _ | _ | Idukki | Project Appraisal under KIIFB in progress