## PROGRESS TEMPLATE
KERALA STATE CONSTRUCTION CORPORATION
KIIFB-Project Progress Report as on 27.05.2020-Registration Department Works
Sl No: | SPV | Project Code | Project Name | Sub-Project Name | Package Name/Package code | District | Accepted Tender Amount (Cr) | Name of Contractor | Duration of work (Months) | Date of Commencement | Due date of completion | Extended date of completion | Expected date of completion | Current Progress in Detail | Planned | Achieved
1 | KSCC | RGD007-05 | Construction of Building for Sub Registrar offices | SUB REGISTRAR OFFICE KANYAKULANGARA | RGD007-05-02 | Trivandrum | 1.01 | Sri. Nelson.J | 12 | 30.01.2019 | 29.01.2020 | 29.07.2020 | 31.10.2020 | FF roof concrete completed. internal and external plastering of GF in progress, plumbing work going on. | 100% | 40% | 40% | _ | _ | Smt.Rema P.K. General Manager in charge-EKM Ph-9497186255 | Ms.Geetha Regional Manager -TVM Ph- 8547912529 | _ | _
2 | KSCC | RGD007-05 | Construction of Building for Sub Registrar offices | SUB REGISTRAR OFFICE KANJIRAMKULAM | RGD007-05-05 | Trivandrum | 0.926 | Sri. T.T Praveen | 12 | 07.01.2019 | 06.01.2020 | 30.04.2020 | 31.10.2020 | Tile work being carried out. | 100% | 60% | 60% | 0.14 | 15 | " | Ms.Geetha Regional Manager -TVM Ph- 8547912529 | Ist and part bill 11.12.2019 | _
3 | KSCC | RGD007-05 | Construction of Building for Sub Registrar offices | SUB REGISTRAR OFFICE NAVAIKULAM | RGD007-05-06 | Trivandrum | 1.37 | Sri. A. Nahas | 12 | 13.03.2019 | 12.03.2020 | 12.07.2020 | 31.07.2020 | Tile work completed. Truss work in Progress | 85% | 80% | 75% | 0.35 | 25 | Smt.Rema P.K. General Manager in charge-EKM Ph-9497186255 | " | Ist and part bill 09.03.2020 | _
4 | KSCC | RGD007-05 | Construction of Building for Sub Registrar offices | SUB REGISTRAR OFFICE MALAYINKEEZHU | RGD007-05-01 | Trivandrum | 1.17 | Smt.Bindhu Sudhakaran | 12 | 16.02.2019 | 15.02.2020 | 15.07.2020 | 31.10.2020 | First floor roof concrete completed | 80% | 50% | 50% | 0.14 | 12 | " | " | Ist and part bill 24.01.2020 | _
5 | KSCC | RGD007-05 | Construction of Building for Sub Registrar offices | SUB REGISTRAR OFFICE ATTINGAL- MAINTENANCE AND REPAIR | RGD007-05-03 | Trivandrum | 0.3145 | Sri. A. Nahas | 6 | 28.02.2019 | 19.08.2019 | 15.10.2019 |  | Work completed | 100% | 100% | 98% | _ | _ | Smt.Rema P.K. General Manager in charge-EKM Ph-9497186255 | Ms.Geetha Regional Manager -TVM Ph- 8547912529 | _ | _
6 | KSCC | RGD007-05 | Construction of Building for Sub Registrar offices | CONSTRUCTION OF NEW BUILDING FOR SUB REGISTRAR OFFICE AT CHIRAYINKEEZHU IN THIRUVANANTHAPURAM DISTRICT | RGD007-05-04 | Trivandrum | 1.31 | _ | 12 | _ | _ | _ |  | Comparitive statement submitted to KIIFB on for approval | _ | _ | _ | _ | _ | " | " | _ | _
7 | KSCC | RGD007-05 | Construction of Building for Sub Registrar offices | CONSTRUCTION OF NEW BUILDING FOR SUB REGISTRAR OFFICE AT THIRUVALLOM THIRUVANANTHAPURAM DISTRICT | RGD007-05 | Trivandrum | 1.71 | [6 empty] | Comparitive statement submitted to KIIFB for approval |  |  | 31% |  |  | Smt.Rema P.K. General Manager in charge-EKM Ph-9497186255 | Sri. Riyad, Regional Manager, Kottayam 9447096155
8 | KSCC | RGD007-05 | Construction of Building for Sub Registrar offices | CONSTRUCTION OF NEW BUILDING FOR SUB REGISTRAR OFFICE AT VARKKALA IN THIRUVANANTHAPURAM DISTRICT | RGD007-05 | Trivandrum | 1.18 | [6 empty] | Building Permit not obtained , pending with CTP. |  |  | 100% | 4502464/- | 40.82% | ,, | ,, | 1st and part bill on 28.02.2020
9 | KSCC |  | Construction of Building for Sub Registrar offices | CONSTRUCTION OF REGISTRATION COMPLEX AT NEMOM in Thiruvananthauram District | RGD007-06 | Trivandrum | 20.88 | _ | _ | _ | _ | _ |  | Detailed estimate submitted to T S Committee for obtaining Technical sanction.T S Committee approved the proposal. Work to be tendered. | -
10 | KSCC | RGD007-04 | Construction of Building for Sub Registrar offices | KIIFB -R D - Construction of New building for Sub Registrar Office Udumbanchola at Mundiyeruma in Idukki District. | RGD007-04-02 | Idukki | 1.1645 | Sri.Francis.P.C, Pulikkal, Kallar.P.O, Thookkupalam, Idukki District. | 12 | 06.12.18 | 05.12.19 | 29.02.2020. | 31.05.2020 | Tile laying in yard and Carparking area are in work progress. | 100% | 98% | 2% | 3366382/- | 23.76% | ,, | ,, | 1st and part bill on 11.02.2020
11 | KSCC | RGD007-04 | Construction of Building for Sub Registrar offices | KIIFB -R D- Construction of New building for Sub Registrar Office at Kaduthuruthy in Kottayam District. | RGD007-04-04 | Kottayam | 1.4 | [6 empty] | The estimate for Rs.140 lakhs is uploaded to KIIFB portal for obtaining revised financial sanction. | [5 empty] | ,, | ,,
12 | KSCC | RGD007-04 | Construction of Building for Sub Registrar offices | KIIFB -R D- Construction of New building for Sub Registrar Office at Thopramkudy in Idukki District. | RGD007-04-01 | Idukki | 1.1031 | Sri.Shine.T.Joseph, Thodukayil House, Thadiyampadu P.O, Manjappara, Idukki District | 12 | 03.12.18 | 02.12.19 | 15.02.2020. |  | Work completed |  | 100%
13 | KSCC | RGD007-04 | Construction of Building for Sub Registrar offices | KIIFB -R D- Construction of Registration Complex in Kottayam District. | RGD007-04-03 | Kottayam | 4.4496 | Sri.Geordy.K. Abraham Kanjiramkunnel Construction 3rd floor, Room No.309 Nirmala Centre, Muvattupuzha. |  | 29.05.2019 | 28.05.2020 |  | 31.03.2021 | Footing and Grade beam completed . Superstructure ..Column work are in progress. |  | 24%
14 | KSCC | RGD007-04 | Construction of Building for Sub Registrar offices | Construction of New Building for Sub Registrar Office at Mararikkulam in Alappuzha Dt | RGD007-04-06 | Alapuzha | 1.83 | M/s Cube India, Kochi. | 12 months | 21.11.18 | 20.11.2019 | 20.05.2020 | 19.09.2020 | Building Structure completed.Tile work going on. Truss work completed.outside and inside painting work progressing Polishing and painting of doors and windows going on.Hand railworks and gate works started.rainwater harvesting work in progress. | 85% | 85% | _ | 0.53 | 29 | Smt.Rema P.K. General Manager in charge-EKM Ph-9497186255 | RAKESH C, REGIONAL MANAGER 9447133269 | 2nd and part bill 19.11.2019 | -
15 | KSCC | - | Construction of Building for Sub Registrar offices | Construction of New Building for Sub Registrar Office at Kollam in Kollam Dt | - | Kollam | - | - | - | - | - | - | - | Due to Non availability of land the changed to chadayamangalam.DPR submitted and waiting for AS approval.
16 | KSCC | RGD007-04 | Construction of Building for Sub Registrar offices | Construction of a new Building for Sub-Registrar office at Kuzhupilly in Ernakulam District | RGD007-04-08 | Ernakulam | 1.15 | Sri.C Georgekutty, Kolenchery | 12 | 2018-12-28 | 2019-12-27 | _ | 30.06.2020 | Floor Tilework in progress | 60% | 60% | 62% | 0.29 | 25 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Beena Nair (Regional Manager) 9633540657 | Ist and part bill 04.01.2020 | _
17 | KSCC | RGD007-04 | Construction of Building for Sub Registrar offices | Construction of a new Building for Sub-Registrar office at Thodupuzha in Idukki District | RGD007-04-09 | Idukki | 1.22 | M/s V J Raju & Company | 12 | 21-12-18 | 10.12.2019 | _ | 30.03.2021 | Fixing of Doors and Windows in progress | 55% | 70% | 55% | 0.38 | 31 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Sri. Riyad, Regional Manager, Kottayam 9447096155 | Ist and part bill 13.01.2020 | _
18 | KSCC | RGD007-04 | Construction of Building for Sub Registrar offices | Construction of a new Building for Sub-Registrar office at Kothamangalam in Ernakulam District | RGD007-04-07 | Ernakulam | 1.52 | Sri.MadhanaMohan | 12 | 25.02.19 | 10.12.2019 | _ | 24.08.2020 | All structural work in GF completed.FF column works completed.Shuttering works for beams and slab of FF in progress. | 25% | 30% | _ | 0.19 | 13 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Beena Nair (Regional Manager) 9633540657 | Ist and part bill 14.02.2020 | _
19 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Akkikkavu | RGD007-03-01 | Thrissur | 0.79 | Sri.M. Velayudhan | 12 | 11.12.2018 | 05.12.2019 | _ |  | Work completed and handed over. | 100% | 100% | 100% | 0.52 | 66 | ,, | Ajith Kumar V V (Regional Manager) 8281882156 | 2nd and part bill 04.01.2020 | _
20 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Kunnamkulam | RGD007-03-04 | Thrissur | 0.81 | Sri.K.J Rajan | 12 | 06.12.2018 | 10.12.2019 | _ |  | Work completed and handed over. | 100% | 100% | 100% | 0.65 | 80 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager) 8281882156 | 3rd and part bill 21.12.2019 | _
21 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Pazhayannur | RGD007-03-07 | Thrissur | 0.583 | Sri.K.M. Abbas | 12 | 11.12.2018 | 10.12.2019 | _ |  | Work completed and handed over. | 100% | 100% | 100% | 0.38 | 65 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager) 8281882156 | 2nd and part bill 23.11.2019 | _
22 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Thrithala | RGD007-03-10 | Palakkad | 0.783 | Sri.M. Velayudhan | 12 | 11.12.2018 | 18.12.2019 | _ |  | Work completed and handed over. | 100% | 100% | _ | _ | _ | Sri. Syamnath Nair, Project Engineer (Electrical) 9447079659 | Ajith Kumar V V (Regional Manager) 8281882156 | _ | _
23 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Kuttippuram | RGD007-03-14 | Malappuram | 0.993 | Sri. Anilkumar | 12 | 19.12.2018 | 19.02.2020 | _ |  | Work completed and handed over. | 100% | 100% | 100% | 0.58 | 59 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager) 8281882156 | 2nd and part bill 30.12.2019
24 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Ottappalam | RGD007-03-11 | Palakkad | 0.862 | Sri.P.V Gopalakrishnan | 12 | 20.02.2019 | 31.07.2020 | _ | 31.07.2020 | Main building painting work and compound wall plastering work in progress. | 95% | 80% | 75.79% | 0.3 | 35 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager) 8281882156 | 2nd and part bill 03.02.2020 | _
25 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Cherpulassery | RGD007-03-12 | Palakkad | 0.798 | Sri.Abuthahir. K. | 12 | 23.01.2019 | 09.10.2020 | _ |  | Work Completed and handed over. | 100% | 100% | 100% | 0.54 | 68 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager) 8281882156 | 2nd and part bill 13.01.2020 | _
26 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Mundur | RGD007-03-13 | Thrissur | 1.15 | Sri.K.N.Biju | 12 | 10.10.2019 | 09.10.2020 | _ | 09.10.2020 | R.C.C plinth beam completed and ground floor columns in progress. | _ | 10% | _ | _ | _ | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager) 8281882156 | _ | _
27 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Tanur | RGD007-03-15 | Malappuram | 0.86 | Sri.M. Velayudhan | 12 | 11.12.2018 | 06.12.2019 | _ |  | Work completed and handed over. | 100% | 100% | 100% | 0.45 | 52 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager) 8281882156 | 2nd and part bill 12.11.2019 | _
28 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Kalpakamchery | RGD007-03-16 | Malappuram | 0.682 | Sri.Anilkumar | 12 | 07.12.2018 | 10.12.2019 | _ |  | Work completed and handed over. | 100% | 100% | 100% | 0.54 | 79 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager) 8281882156 | 2nd and part bill 05.12.2019
29 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Kuzhalmannam | RGD007-03-09 | Palakkad | 0.51 | Sri. Muhammed Basheer | 12 | 11.12.2018 | 10.12.2019 | _ |  | WP(C) No.32911 of 2 vacated on 18.02.2019.Informed contractor to start the work. But again the work had been forcely stopped. The contractor has requested to absolve him from his executed agreement since the site is not hindrance free filed by Sri. Najun Nasar. Stay vacated and work started on 17/9/2019. Half portion reached up to grade beam level. Further work stopped subsequent to the stay order received from Tribunal secretary, Tribunal for Local Self Govt. Institutons. | _ | _ | _ | _ | _ | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager) 8281882156 | _ | _
30 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Kallettumkara | RGD007-03-03 | Thrissur | 1.14 | Sri. K.M. Ashraf | 12 | 25.01.2019 | 31.07.2020 | _ | 31.07.2020 | Outside plastering and Tile laying in progress | 100% | 75% | 41% | 0.37 | 32 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager) 8281882156 | 1st and part bill 03.02.2020
31 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Triprayar | RGD007-03-05 | Thrissur | 0.98 | _ | 12 | _ | _ | _ |  | One of the bidders, Sri. Unnikrishnan T, having MSME registration has filed a case against KSCC so agreement could not be executed till date. Now case disposed and direction given to contractor to start the work | _ | _ | _ | _ | _ | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager) 8281882156 | _
32 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB-Construction of Sub-Registrar office, Andathode | RGD007-03-02 | Thrissur | 0.112 | Sri.K.J Rajan | 12 | _ | 02.07.2019 | _ |  | Since the bearing capacity of the soil at 1.2m below is found to be very weak, foundation design is necessitated to be changed to pile foundation. Hence estimated cost increased. Revised estimate has been prepared and submitted. Awaiting sanction for Rs. 172.62 lakhs from KIIFB | _ | __ | _ | _ | _ | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | -
33 | KSCC | RGD007-01 | Construction of Building for Sub Registrar offices | KIIFB- Construction of District Registrar office,Mananchira in kozhikode district. AS Amt.Rs.267.70Lakh | RGD007-01-01 | Kozhikode | 1.97 | K.Anilkumar, Karuvisserry P.O, Kozhikkode | 12 | 16.11.2019 | 15.11.2020 | _ | 15.06.2021 | Pile work in progress. | 15 | 5 | 33 | 0.0099 | Nil | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | Nil | Nil
34 | KSCC | RGD007-01 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Westhill in kozhikode district. AS Amt. Rs.156.40 Lakh | RGD007-01-02 | Kozhikode | 1.41 | Shameer.K, Areacode, Malappuram | 12 | 03.07.2019 | 02.07.2020 |  | 31.12.2020 | Pile Cap and Plinth beam concreting completed.Column GF in progress. | 15 | 15 | 100 | 0.021 | 10.43 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | 1st & part bill Amount on 06.04.2020 | Nil
35 | KSCC | RGD007-02 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Chelannur, in kozhikode district. AS Amt. Rs.133.10 Lakh | RGD007-02-03 | Kozhikode | 1.13 | Sri.Abdul Majeed.P, | 12 | 28.02.2019 | 27.02.2020 |  | 30.06.2020 | Finishing work in progress | 80 | 70 | 88 | 0.079 | 18.43 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | 11st & part bill on 17.12.2019 | 30.05.2020
36 | KSCC | RGD007-02 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Chathamangalam, in kozhikode district. AS Amt. Rs.105.50 Lakh | RGD007-02-02 | Kozhikode | 0.84 | Sri.Abdul Majeed.N, | 12 | 23.08.2019 | 22.08.2020 |  | 31.12.2020 | Earth wok excavation completed. | 20 | 10 | 10 | 0.0017 | Nil | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | _
37 | KSCC | RGD007-02 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Azhiyur in kozhikode district. AS Amt.Rs. 110.30 Lakh | RGD007-02-01 | Kozhikode | 0.97 | Devaraj, Rajanilayam, Uliyil P.O, Kannur | 12 | 12.09.2019 | 11.09.2020 |  | 31.12.2020 | Lintel Sunshade in GF completed. GF slab work in progress. | 40 | 25 | 63 | 0.024 | 8.95 | " | Ajith Kumar V V (Regional Manager), 8281882156 | 1st & part bill on 06.04.2020 | Nil
38 | KSCC | RGD007-02 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Nadapuram, in kozhikode district.AS Amt.Rs.110.30 Lakh | RGD007-02-05 | Kozhikode | 0.92 | M/s. Selmec Engineering Constructions, | 12 | 23.02.2019 | 22.02.2020 | 06.04.2020 | 15.08.2020 | Plastering work & finishing workin progress. | 75 | 60 | 80 | 0.55 | 36.84 | " | Ajith Kumar V V (Regional Manager), 8281882156 | 2 nd & part bill on 06.02.2020 | Nil
39 | KSCC | RGD007-02 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Naduvannur, in kozhikode district. AS Amt. Rs.111.20 Lakh | RGD007-02-06 | Kozhikode | 0.89 | Sri.Shameer.K | 12 | 25.01.2019 | 24.01.2020 | 23.02.2020 |  | Work completed. |  | 100 |  |  | 73.1 | " | Ajith Kumar V V (Regional Manager), 8281882156 | 2nd & part bill on 12.11.2019 | Nil
40 | KSCC | RGD007-02 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Thiruvallur in kozhikode district. AS Amt. Rs. 109.40 Lakh | RGD007-02-09 | Kozhikode | 0.97 | M/s. Madathumbhagom Labour Contract Co-operative Society, | 12 |  |  |  |  | Work order issued. Agreement to be executed. A Court case regarding tender acceptance is raised.Case disposed direction issued to the contractor to start the work | [5 empty] | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | _ | Nil
41 | KSCC | RGD007-02 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Perambra in kozhikode district. AS Amt. Rs. 108.70 Lakh | RGD007-02-08 | Kozhikode | 0.92 | Sri.Safeer.K | 12 | 21.12.2019 | 20.12.2020 |  |  | Work completed & inagurated. |  | 100 |  |  | 0.92 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | 3 nd & part bill on 03.02.2020 | Nil
42 | KSCC | RGD007-02 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Payyoli in kozhikode district. AS Amt. Rs. 115.23 Lakh | RGD007-02-07 | Kozhikode | 0.9 | Sri. Shebin Sreedharan | 12 | 04.02.2019 | 03.02.2020 |  |  | Work completed & inagurated. |  | 100 |  |  | 71.65 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | 3 nd & part bill on 28.02.2020 | Nil
43 | KSCC | RGD007-02 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Feroke in kozhikode district. AS Amt. Rs.119.80 Lakh | RGD007-02-04 | Kozhikode | 1.09 | M/s. Selmec Engineering Constructions | 12 | 23.08.2019 | 22.08.2020 |  | 22.12.2020 | Column GFand Retaining wall work completed. Column shuttering work in progress. | 50 | 20 | 40 | 0.02 | _ | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | Nil | Nil
44 | KSCC | RGD007-02 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Villiappally in kozhikode district. AS Amt. Rs.114.50Lakh | RGD007-02-10 | Kozhikode | 1.02 | Sri.Shebin Sreedharan | 12 | 27.06.2019 | 26.06.2020 |  | 30.09.2020 | Structure completed finishing work in progress. | 80 | 60 | 75 | 0.612 | 8.48 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | 1st & part bill on 03.02.2020 | Nil
45 | KSCC | RGD007-02 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Thenjipalam in Malappuram District. AS Amt. Rs.73.50 Lakh | RGD007-02-11 | Malappuram | 0.55 | Sri.Abdul Majeed.N | 12 | 20.12.2018 | 19.12.2019 |  |  | Work completed & inagurated. |  | 100 |  |  | 64.9 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | 3 nd & part bill on 29.01.2020 | Nil
46 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Malappuram in Malappuram District. | RGD007-03-06 | Malappuram | 1.01 | M/s. Manzil Constructions | 12 | 03.07.2019 | 02.07.2020 |  | 31.12.2020 | GF column works in completed. | 20 | 10 | 50 | 0.01 |  | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | _
47 | KSCC | RGD007-03 | Construction of Building for Sub Registrar offices | KIIFB- Construction of Sub Registrar office Parappanangadi in Malappuram District. | RGD007-03-08 | Malappuram | 1.123 | Sri. K Anil Kumar | 12 |  |  |  |  | Revised estimate for foundation revision submitted to KIIFB for approval | [5 empty] | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), 8281882156 | _
48 | KSCC | RGD007-01 | Construction of Building for Sub Registrar offices | Construction of New Building for Sub - Registrar Office at Mananthavadi in Wayanad District | RGD007-01-07 | Wayanad | 1.03 | Sri. Mohammed Shafi. P, Parayangadan House, Muthiraparamba, Valluvamram PO, Malappuram - 676 517 | 12 | - |  | - |  | Work order issued. Agreement to be executed. A Court case regarding tender acceptance is raised.Now Case disposed and directed contractor to start work | - | _ | - | _ | _ | " | Sri. Roy. P.S, Regional Manager, KSCC, Kannur 9447716468 | - | -
49 | KSCC | RGD007-01 | Construction of Building for Sub Registrar offices | Construction of New Building for Sub-Registrar Office at Thaliparamba in Kannur District | RGD007-01-03 | Kannur | 0.896 | Sri. Boby Sebastian, Valuvettickal House, Kelakom PO, Mattannur, Kannur | 12 | 07.01.2019 | 06.01.2020 | 31.03.2020 | 31.07.2020 | plastering work 90% completed.Septic Tank,rain water tank work completed.plumbing work in progress.window grill fixing in progress | - | 75% | - | 0.43 | 48 | " | Sri. Roy. P.S, Regional Manager, KSCC, Kannur 9447716468 | 2nd and part bill 06.04.2020 | _
50 | KSCC | RGD007-01 | Construction of Building for Sub Registrar offices | Construction of New Building for Sub-Registrar Office at Uliyil in Kannur District | RGD007-01-04 | Kannur | 1.04 | B.Mohammed Haji, Baladukka, Chengala, Kasargode | 12 | 02.09.2019 | 01.09.2020 | - | 30.11.2020 | structural work upto plinth beam completed. Basement floor slab shuttering in progress. Boundary Retaining wall RR work in progress | - | 18% | - | _ | _ | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | -do- | - | -
51 | KSCC | RGD007-01 | Construction of Building for Sub Registrar offices | Construction of New Building for Sub Registrar office at Trikkaripur in Kasargod district | RGD007-01-05 | Kasaragod | 0.72 | Sri. Mohammed Harish B A, Najath House, Baladukka, Nekreje PO, Kasaragod - 671 543 | 12 | 25.09.2019 | 24.09.2020 | - | 23.12.2020 | G.Floor slab concreting completed | - | 20% | - | _ | _ | " | -do- | - | -
52 | KSCC | RGD007-01 | Construction of Building for Sub Registrar offices | Construction of New Building for Sub Registrar office at Uduma in Kasargod district | RGD007-01-06 | Kasaragod | - | - | - | - | - | - |  | As per GO(M.s) No.6 /2020/AGRI dated 14/01/2020 sanction obtained from Govt of Kerala for wet land conversion.Revised AS to be sanctioned from KIIFB | - | 0% | - | _ | _ | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Sri. Roy. P.S, Regional Manager, KSCC, Kannur 9447716468 | _ | -