## Sheet1
KIIFB WORKS (DEPARTMENT WISE DETAILS)
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14
PROGRESS REPORT OF REGISTRATION DEPARTMENT-01/07/2020
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Sl.No | Name Of Project | District | Area (in m²) | AS Amount | TS Amount | Name of Contractor | PAC | Electrification Amount | D/o Commencement | Original TOC | Extented TOC | Expected TOC | Status | Percentage of Progress | Remarks
REGION -KOZHIKODE
1 | KIIFB- Construction of District Registrar office Manachira in Kozhikode district. | Kozhikode | 788.8 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.27670000/- | APEKKD/2018-2019/2017/11077 DT.27.07.2018 Amt. Rs.27626983/- | Civil - Sri. K. Anilkumar | 220.28 Lakh | 55.99 Lakh | 16.11.2019 | 15.11.2020 | nil | 15.06.2021 | Pile work started. Now stopped due to non-availability of Labour in covid 19 Lockdown. | 5%
2 | KIIFB- Construction of Sub Registrar office westhill in Kozhikode district. | Kozhikode | 523.36 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.15640000/- | APEKKD/2018-2019/2018/215 DT.27.07.2018 Amt. Rs.15635373/- | Civil - Sri. Shameer. K | 143.39 Lakh | 12.95 Lakh | 03.07.2019 | 02.07.2020 | nil | 31.12.2020 | Column GF completed GF slab shuttering work in progress. | 15%
3 | KIIFB- Construction of Sub Registrar office Azhiyur in Kozhikode district. | Kozhikode | 416.63 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.11030000/- | APEKKD/2018-2019/2018/212 DT.27.07.2018 Amt. Rs.11022424/- | Civil - Sri. Devaraj P.R | 97.54 Lakh | 12.68 Lakh | 12.09.2019 | 11.09.2020 | nil | 31.12.2020 | Lintel Sunshade completed.GF slab work in progress. | 25%
4 | KIIFB- Construction of Sub Registrar office Chathamangalam in Kozhikode district. | Kozhikode | 416.63 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.10550000/- | APEKKD/2018-2019/2018/190 DT.27.07.2018 Amt. Rs.10547629/- | Civil - Sri. Abdul Majeed. N | 92.79 Lakh | 12.68 lakh | 23.08.2019 | 22.08.2020 | nil | 31.12.2020 | PCC completed. RCC footing in progress. | 4%
5 | KIIFB- Construction of Sub Registrar office Chelannur in Kozhikode district. | Kozhikode | 551.61 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.13310000/- | APEKKD/2018-2019/2018/232 DT.27.07.2018 Amt. Rs.13306325/- | Civil-Sri. Abdul Majeed.P. Electrical- Sri. Narayanan | 119.88 Lakh | 13.17 Lakh | 28.02.2019 | 27.02.2020 | nil | 31.07.2020 | Finishing work in progress. | 70%
6 | KIIFB- Construction of Sub Registrar office Payyoli in kozhikode district. | Kozhikode | 491.17 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.11522789/- | APEKKD/2018-2019/2018/178 DT.27.07.2018 Amt. Rs.11521697 | Civil-Sri. Shebin Sreedharan. Electrical- S. Suresh, M/S Mecho Electricals | 102.14 Lakh | 13.08 lakh | 04.02.2020 | 03.02.2020 |  |  | Completed. Work not hand over because Dump waiter work is balance | 100% | Inaugurated
7 | KIIFB- Construction of Sub Registrar office Nadapuram in Kozhikode district. | Kozhikode | 416.63 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.11030000/- | APEKKD/2018-2019/2018/211 DT.27.07.2018 Amt. Rs.11009368/- | Civil-M/S. Selmec Engineering constructins. Electrical- Sri. Sajithlal | 97.41 Lakh | 12.68 lakh | 23.02.2019 | 22.02.2020 |  | 31.08.2020 | Plastering work & finishing work in progress. | 60%
8 | KIIFB- Construction of Sub Registrar office Villyapalli in Kozhikode district. | Kozhikode | 416.63 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.11450000/- | APEKKD/2018-2019/2018/207DT.27.07.2018 Amt. Rs.11446128/- | Civil-Sri. Shebin Sreedharan. Electrical- Sajithlal | 101.55 Lakh | 12.9 lakh | 03.07.2019 | 02.07.2020 | nil | 31.12.2020 | Structure completed. Plastering work in progress. | 70%
9 | KIIFB- Construction of Sub Registrar office Perambra in kozhikode district. | Kozhikode | 416.63 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.10870000/- | APEKKD/2018-2019/2018/208 DT.27.07.2018 Amt. Rs.10939829/- | Civil-Sri. Safeer. K. Electrical-S. Suresh, M/S Mecho electricals | 95.63 Lakh | 13.05 lakh | 21.12.2019 | 20.12.2020 |  |  | Completed. Work not hand over because Dump waiter work is balance | 100% | Inaugurated
10 | KIIFB- Construction of Sub Registrar office Thiruvallur in kozhikode district. | Kozhikode | 416.63 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.10940000/- | APEKKD/2018-2019/2018/210 DT.27.07.2018 Amt. Rs.10868776/- | Civil-Madathumbagam labour contract co-operative society | 96.71 Lakh | 12.67 lakh |  |  |  |  | Court case disposed. Work order issued. Informed to the contractor to execute Agreement.
11 | KIIFB- Construction of Sub Registrar office Naduvannur in Kozhikode District | Kozhikode | 416.63 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.11120000/- | APEKKD/2018-2019/2018/209 DT.27.07.2018 Amt. Rs.11115804/- | Civil-Sri. Shameer. K. Electrical- Narayanan | 98.47 Lakh | 12.68 lakh | 25.01.2019 | 24.01.2020 | 23.02.2020 |  | Completed. Work not hand over because Dump waiter work is balance. | 100% | Not inaugurated
12 | KIIFB- Construction of Sub Registrar office Ferook in Kozhikode district | Kozhikode | 438.56 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.11980000/- | APEKKD/2018-2019/2018/193 DT.27.07.2018 Amt. Rs.11974593/- | Civil-M/S. Selmec Engineering constructins | 106.84 Lakh | 12.9 lakh | 23.08.2019 | 22.08.2020 | nil | 31.12.2020 | GF slab shuttering work in progress. | 30%
13 | KIIFB- Construction of Sub Registrar office Thenjipalam in Malappuram District. | Malappuram | 205.24 | RGD007-02-PA-01 dt.03.07.2018 Amt. Rs.7350000/- | APEKKD/2018-2019/2018/187 DT.26.07.2018 Amt. Rs.7200599/- | Civil-Sri. N. Abdul Majeed. Electrical-S.Suresh, M/S Mecho electricals | 59.35 Lakh | 12.65 lakh | 20.12.2018 | 19.12.2018 |  |  | Completed. Work not hand over because Dump waiter work is balance. | 100% | Inaugurated
14 | KIIFB- Construction of Sub Registrar office Malappuram in Malappuram district. . | Malappuram | 362.3 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.13760000/- | APE2TSR/2018-2019/2018/122 DT.28.07.2018 Amt. Rs.128.70 LAKH | Civil- M/S. Manzil constructions | 115.67 Lakh | 13.03 lakh | 03.07.2019 | 02.07.2020 | nil | 31.12.2020 | GF slab work completed. | 25%
15 | KIIFB- Construction of Sub Registrar office Parappanagadi in Malappuram district. . | Malappuram | 394.83 | G.O.(Rt) No. 995/2017 Tax Dept. dt.05.12.2017 Amt. Rs.13000000/- | APE1TSR/2018-2019/2018/2190 Dated 28.07.2018 Amt. Rs.13759671/- | Civil -Sri. K. Anilkumar | 124.60 Lakh | 12.99 lakh |  |  |  |  | Revised Esstimate submitted to KIIFB.
REGION -ERNAKULAM
16 | KIIFB – Construction of New Building for Sub – Registrar Office at Thodupuzha in Idukki District | IDUKKI | 418.39 | 141.21 Lakh | 141.21 Lakh | Civil-M/s V J Raju & Company Electrical-Shri. A R Sivashankaran | 122.7 Lakh | 12.97 lakh | 21.12.2018 | 20.12.2019 | 30.06.2020 | 30.09.2020 | Sanitarey fitting and primer coating in progress | 80%
17 | KIIFB – Construction of New Building for Sub – Registrar Office at Kuzhupilly in Ernakulam District | ERNAKULAM | 335.34 | 137.2 Lakh | 137.2 Lakh | Civil-Shri. C GeorgeKutty Electrical-M/s Elight complete Networking Solutions | 115.09 Lakh | 13.05 lakh | 28.12.2018 | 27.12.2019 | 30.06.2020 | 30.09.2020 | Electrical works in progress. | 77%
18 | KIIFB – Construction of New Building for Sub – Registrar Office at Kothamangalam in Ernakulam District | ERNAKULAM | 472.65 | 186.8 Lakh | 186.7 Lakh | Civil-Shri. Madhanamohanan K R Electrical-M/s Elight complete Networking Solutions | 152.37 Lakh | 13.17 lakh | 25.02.2019 | 24.02.2020 | 24.08.2020 | 24.12.2020 | Columns beams and slab in GF,FF completed. GF lintel and solid block work in progress | 50%
REGION -KANNUR
19 | Construction of New Building for Sub - Registrar Office at Mananthavadi in Wayanad District | Wayanad | 365.69sqm | 121.70 Lakh | 121.70 Lakh | Sri.Muhammed Shafi.P Parayangadan House, Muthiraparamba Valluvamram P.O, Malappuram-676517 | 102 Lakh | 12.65lakh | _ | _ | _ | _ | Court case disposed. Work order issued.Earthwork Excavation for site levelling started. | _
20 | Construction of New Building for Sub-Registrar Office at Thaliparamba in Kannur District | Kannur | 462sqm | 121.20 Lakh | 121.20 Lakh | Sri. Boby Sebastian, Valuvettickal House, Kelakom PO, Mattannur, Kannur | 89 Lakh | 13.01 lakh | 07.01.2019 | 06.01.2020 | 31.03.2020 | 31.07.2020 | External plumbing work in progress.Terrace floor-roof column work in progress.Gate fixing in progress | 82%
21 | Construction of New Building for Sub-Registrar Office at Uliyil in Kannur District | Kannur | 531.63sqm | 136 Lakh | 146.70 Lakh | Sri. B. Muhammed Haji,Baladukka, Chengala,Kasargod | 104 Lakh | 12.91 lakh | 02.09.2019 | 01.09.2020 | _ | 30.11.2020 | Basement floor -roof slab concreting completed.Ground floor column work in progress | 22%
22 | Construction of New Building for Sub Registrar office at Trikkaripur in Kasargod district | Kasargod | 305.05sqm | 91.10 Lakh | 91.10 Lakh | Sri. Muhammed Harish. B.A, Najath (H), Baladkka, Kasaragod | 72.30 Lakh | 12.58 lakh | 25.09.2019 | 24.09.2020 | _ |  | First Floor Slab Centering and shuttering in progress | 30%
23 | Construction of New Building for Sub Registrar office at Uduma in Kasargod district | Kasargod | 357.14sqm | 106.20 Lakh | _ |  | _ | 12.88 lakh | _ | _ | _ | _ | Awaiting for Revised Administrative Sanction from KIIFB. | _ | _
REGION -KOTTAYAM
24 | Construction of Registration Complex in Kottayam District. | Kottayam | 1194m2 | 626 Lakh | 589 Lakh | Sri.Geordy.K. Abraham Kanjiramkunnel Construction 3rd floor, Room No.309 Nirmala Centre, Muvattupuzha. | 444.96 Lakh | 68.65 lakh | 29.05.19 | 28.05.2020 |  | 31.12.2020 | Ground floor slab shuttering is in progress | 28%
25 | Construction of New building for Sub Registrar Office at Thopramkudy in Idukki District. | Idukki | 298.05m2 | 140 Lakh | 137 Lakh | Sri.Shine.T.Joseph, Thodukayil House, Thadiyampadu P.O, Manjappara, Idukki District | 110.31 Lakh | 13.06 lakh | 03.12.18 | 02.12.19 | 15.02.2020 |  | civil work completed | 100% | Not inaugurated
26 | Construction of New building for Sub Registrar Office Udumbanchola at Mundiyeruma in Idukki District. | Idukki | 389.29m2 | 145 Lakh | 141 Lakh | Sri.Francis.P.C, Pulikkal, Kallar.P.O, Thookkupalam, Idukki District. | 116.45 Lakh | 13.20 lakh | 06.12.18 | 05.12.19 | 29.02.2020 | 20.06.20 | civil work completed | 99% | Not inaugurated
27 | Construction of New building for Sub Registrar Office at Kaduthuruthy in Kottayam District. | Kottayam | 474.21m2 | 140 Lakh | _ |  | _ | 12.86 lakh |  |  |  |  | TS issued. Work tendered
REGION -TRISSUR
28 | KIIFB-Construction of Sub-Registrar office, Mundoor | Thrissur | 543.53 | 129.64 Lakh | 129.63 Lakh | Sri: KN Biju | 109.45 Lakh | 13.18 lakh | 10.10.2019 | 09.10.2020 | 09.10.2020 | 09.10.2020 | Ground floor beams and slabs reinforcement work in progress | 20%
29 | KIIFB-Construction of Sub-Registrar office, Kallettumkara | Thrissur | 541.54 | 131.63 Lakh | 131.63 Lakh | Sri:KM Ashraf | 113.98 Lakh | 12.99 lakh | 11.12.2018 | 05.12.2019 | 30.08.2020 | 30.08.2020 | Window shutter fixing completed.,Roof truss work completed. Painting work and interlock laying in progress. | 90%
30 | KIIFB-Construction of Sub-Registrar office, Ottapalam | Palakkad | 345.59 | 110.20 lakhs | 110.17 Lakh | Sri:Gopalakrishnan PV | 86.24 Lakh | 12.96 lakh | 20.02.2019 | 31.07.2020 | 31.07.2020 | 31.07.2020 | Painting work in progress.Aluminium work in progress | 90%
31 | KIIFB-Construction of Sub-Registrar office, Kuzhalmannam | Palakkad | 222.85 | 59.32 Lakh | 59.32 Lakh | Sri:Muhammed Basheer | 50.64 Lakh | Half portion beams reched up to beam level. |  |  |  |  | WP(C) No.32911 of 2 vacated on 18.02.2019.Informed contractor to start the work. But again the work had been forcely stopped. The contractor has requested to absolve him from his executed agreement since the site is not hindrance free filed by Sri. Najun Nasar. Stay vacated and work started on 17/9/2019. Half portion reached up to grade beam level. Further work stopped subsequent to the stay order received from Tribunal secretary, Tribunal for Local Self Govt. Institutons. | ___
32 | KIIFB-Construction of Sub-Registrar office, Andathode | Thrissur | 539.9 | 132.64 Lakh | 132.64 Lakh | Sri : KJ Rajan | 111.88 Lakh | 13.09 lakh |  |  |  |  | Since the bearing capacity of the soil at 1.2m below is found to be very weak, foundation design is necessitated to be changed to pile foundation. Hence estimated cost increased. Revised estimate has been prepared and submitted. Awaiting for Technical sanction for Rs. 172.62 lakhs from KIIFB | ___
33 | KIIFB-Construction of Sub-Registrar office, Thriprayar | Thrissur | 105.93 | 118.80 Lakh | 118.77 Lakh | Sri: OB Baburaj | 97.79 Lakh | 12.85 lakh | ___ | ___ | ___ | ___ | Court case disposed. Work order issued. Agreement executed on 26/06/2020 | ___
34 | KIIFB-Construction of Sub-Registrar office, Akkikkavu | Thrissur |  | G.O(Rt)No:/995/2017/Tax Dept Dated 05/12/2017 | 98.9lakhs | Sri.M. Velayudhan | 79 Lakh | 12.85 lakh | 11.12.2018 | 05.12.2019 |  |  | Work completed and handed over. | 100%
35 | KIIFB-Construction of Sub-Registrar office, Kunnamkulam | Thrissur |  | G.O(Rt)No:/995/2017/Tax Dept Dated 05/12/2018 | Rs98.90 lakhs | Sri.K.J Rajan | 81 Lakh | 12.99 lakh | 06.12.2018 | 10.12.2019 |  |  | Work completed and handed over. | 100%
36 | KIIFB-Construction of Sub-Registrar office, Pazhayannur | Thrissur |  | G.O(Rt)No:/995/2017/Tax Dept Dated 05/12/2019 | Rs 70.3 lakhs | Sri.K.M. Abbas | 58.30 Lakh | 6.16 lakh | 11.12.2018 | 10.12.2019 |  |  | Work completed and handed over.
37 | KIIFB-Construction of Sub-Registrar office, Thrithala | Palakkad |  | G.O(Rt)No:/995/2017/Tax Dept Dated 05/12/2020 | Rs 96.98 lakhs | Sri.M. Velayudhan | 78.30 Lakh | 12.76 lakh | 11.12.2018 | 18.12.2019 |  |  | Work completed and handed over. |  | Not inaugurated
38 | KIIFB-Construction of Sub-Registrar office, Kuttippuram | Malappuram |  | G.O(Rt)No:/995/2017/Tax Dept Dated 05/12/2021 | Rs 1.28 Cr | Sri. Anilkumar | 99.30 Lakh | 13.18 lakh | 19.12.2018 | 19.02.2020 |  |  | Work completed and handed over.
39 | KIIFB-Construction of Sub-Registrar office, Cherpulassery | Palakkad |  | G.O(Rt)No:/995/2017/Tax Dept Dated 05/12/2022 | Rs 1.1Cr | Sri.Abuthahir. K. | 79.80 Lakh | 12.96 lakh | 23.01.2019 | 09.10.2020 |  |  | Work Completed and handed over.
40 | KIIFB-Construction of Sub-Registrar office, Tanur | Malappuram |  | G.O(Rt)No:/995/2017/Tax Dept Dated 05/12/2023 | Rs 99.17 lakhs | Sri.M. Velayudhan | 86 Lakh | 13.18 lakh | 11.12.2018 | 06.12.2019 |  |  | Work completed and handed over.
41 | KIIFB-Construction of Sub-Registrar office, Kalpakamchery | Malappuram |  | G.O(Rt)No:/995/2017/Tax Dept Dated 05/12/2024 | Rs 88.1 Lakhs | Sri.Anilkumar | 68.20 Lakh | 13.18 lakh | 07.12.2018 | 10.12.2019 |  |  | Work completed and handed over.
REGION -TVM
42 | Registration Department - Construction of New Buildng for Sub registrar Office Kanyakulangara | TVM | 255.00 sqm | GO(Rt) No.995/2017/TD dt 05.12.2017 | APETVPM/2018-19/2018/241 dt 27.07.2018 for an amount of Rs.1,13,30,000/- | Sri.T.Nelson | 99 Lakh | 12.61 lakh | 30.01.2019 | 29.01.2020 | 29.07.2020 | 31.10.2020 | 1st floor roof slab concrete completed, Masonry in FF and GF completed. Masonry work for compound wall completed. Internal plastering of GF completed. External plastering is in progress. Lintel slab and rack slab in FF completed. Water supply and sanitary work in progress | 70%
43 | Registration Department-Construction of New Buildng for Sub registrar Office Kanjiramkulam | TVM | 516.00 sqm | GO(Rt) No.995/2017/TD dt 05.12.2017 | APETVPM/2018-19/2018/238 dt 27.07.2018 for an amount of Rs.98,782,00/- | T.T. Praveen | 77 Lakh | 6.18 lakh | 07.01.2019 | 06.01.2020 | 30.04.2020 | 31.10.2020 | Flooring work completed, Joinery work goingon | 70%
44 | Registration Department - Construction of New Buildng for Sub registrar Office Navaikulam | TVM | 699.00 sqm | GO(Rt) No.995/2017/TD dt 05.12.2017 | APETVPM/2018-19/2018/244 dt 27.07.2018 for an amount of Rs.1,50,18,300/- | Sri.A.Nahas | 127 Lakh | 16.10 lakh | 13.03.2019 | 12.03.2020 | 12.05.2020 | 31.07.2020 | External and Internal plastering completed, Fabrication work for roof truss has completed, Tile work completed. Septic tank work completed. Finishing work going on. | 85%
45 | Registration Department-Construction of New Buildng for Sub registrar Office Malayinkeezhu- | TVM | 403.00 sqm | GO(Rt) No.995/2017/TD dt 05.12.2017 | APETVPM/2018-19/2018/236 dt 27.07.2018 for an amount of Rs.1,29,80,300 | Smt.Bindhu Sudhakaran | 109 Lakh | 12.77 lakh | 16.02.2019 | 15.02.2020 | 15.07.2020 | 31.10.2020 | FF roof slab concrete completed | 50%
46 | SUB REGISTRAR OFFICE ATTINGAL- MAINTENANCE AND REPAIR | TVM | 180 sqm | GO(Rt) No.995/2017/TD dt 05.12.2017 | Civil-APETVPM/2018-19/2018/235 dt 27.07.2018 for an amount of Rs.45,40,00/- Electrical- APETVPM/2018-19/2019/657 dt 28.02.2019 for an amount of Rs.1,08,600- | Civil-Sr.A.Nahas Electrical-Sri.Velappan Nair | 31 Lakh | 1.08 lakh | 28.02.2019 | 19.08.2019 | 15.10.2019 |  | Work completed. 1st & Final bill not submitted to KIIFB. | 100% | Electrical-Work Completed Bill Not submitted
47 | Registration Department - Construction of New Buildng for Sub registrar Office Chirayinkeezhu | TVM | 519.00sqm | GO(Rt) No.995/2017/TD dt 05.12.2017 | … | … | … | 13.10 lakh | … | … | … | … | TS issued. Work tendered
48 | Registration Department - Construction of New Buildng for Sub registrar Office at Thiruvallom in Thiruvanathapuram | TVM | 328sqm | GO(Rt) No.995/2017/TD dt 05.12.2017 | … | … | … | 12.91 lakh | … | … | … | … | Revised Estimate submitted to KIIFB for revised TS
49 | Registration Department- Construction of New Buildng for Sub registrar Office at Varkala in Thiruvanathapuram | TVM | 454.00sqm | GO(Rt) No.995/2017/TD dt 05.12.2017 | … | … | … | 12.95 Lakh | … | … | … | … | Building Permit not obtained , pending with CTP
50 | CONSTRUCTION OF REGISTRION COMPLEX AT NEMOM | TVM | 5152.00sqm | GO(Rt) No.995/2017/TD dt 05.12.2017 for an amount of Rs.20.88 crore | APETVPM/2020-2021/CC/2018/1737 dt 06.06.2020 for an amount of Rs.20.88 crore | … | … |  | … | … | … | … | TS issued. Work tendered
REGION -ALPY
51 | Construction of Sub registrar office at Mararikulam | Alappuzha | 495.05 | 209 Lakh | 209 Lakh | Sri.Asharaf(civil) ,Sri Arun(Electrical) | 202.19 Lakh | 6.71 lakh | 21-11.2018 | 2019-11-20 | 2020-08-19 | NA | Building works completed.Rain water harvesting Tank and compound wall works going on. | 90%
52 | Construction of sub registrar office at Chadayamangalam | Kollam | 555.42 | [9 empty] | Estimate submitted to Sub Registrar Chadayamangalam for getting Administrative Sanction. |  | Estimate amount Rs2.483 cr