## PROGRESS TEMPLATE
KERALA STATE CONSTRUCTION CORPORATION-HOME DEPARTMENT DATE-07/09/2020
Sl No: | SPV | Project Code | Project Name | Package Name/Package code | District | Total Estimate Amount (Cr) | Contract PAC (Cr) | Name of Contractor | Duration of work (Months) | Date of Commencement | Due date of completion | Extended date of completion | Expected date of completion | Current Progress in Detail(07/09/2020) | Planned | Achieved |  |  |  | Project Cost
1 | KSCC | HOM001-01 | Construction of Court Complex at Thalassery in Kannur District | HOM001-01-02 Construction of Court Complex at Thalasserry under KIIFB - Civil works | Kannur | 55 | 37.22 | A.M.Muhammad Ali | 24 | -- |  | - | 30.06.2022 | Agreement executed for civil works Preparatory works at site in progress. | - | 0% | - | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Sri. Roy. P.S, Regional Manager, KSCC, Kannur 9447716468
2 | KSCC | HOM001-02 | Construction of Court Complex at Koothuparamba in Kannur District | _ | Kannur | 25 | _ | _ | _ | -- | -- | -- | -- | DPR submitted to KIIFB for approval on 07.03.2020 | _ | 0% | _ | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Sri. Roy. P.S, Regional Manager, KSCC, Kannur 9447716468
3 | KSCC | HOM001-05 | Construction of Court Complex at Nedumkamdam in Idukki District | _ | Idukki | 33.17 | _ | _ | _ | _ | _ | _ | _ | DPR submitted to KIIFB for approval on 22.06.2020 |  | 0%
4 | KSCC | HOM001-06 | Construction of Court-Complex at Peerumedu in Idukki District | _ | Idukki | 29.96 | _ | _ | _ | _ | _ | _ | _ | DPR submitted to KIIFB for approval on 15.07.2020 |  | 0%
5 | KSCC | HOM001-03 | Construction of Court Complex at Ranni in Pathanamthitta District | _ | Pathanamthitta | 26.42 | _ | _ | _ | _ | _ | _ | _ | DPR submitted to KIIFB for approval on 13.03.2020 |  | 0%
6 | KSCC | HOM001-04 | Construction of Court Complex at Palakkad in Palakkad District | _ | Palakkad | 68.33 | _ | _ | _ | _ | _ | _ | _ | DPR submitted to KIIFB for approval 18.03.2020 |  | 0%