## SCDD
KIIFB-Project Progress Report as on 28.07.2020-SC Development Department Works-SPV-KSCC Ltd
[17 empty] | Physical Progress (%) | Physical Progress (%) | Physical Progress (%) | Financial Progress (in Cr) | Percentage of Bill Amount Sanctioned (%) | PMU Head Name & Contact No: | Project-in-charge Name & Contact No: | Last Bill details | Tendative Date for the next bill Due
Sl No: | Project Code | Project Name | District | Buillt up Area in (m2) | A S Amount in (Lakhs) | Final T S Amount in (Lakhs) | Agreed PAC (Cr) | Name of Contractor | Duration of work (Months) | Site hand over Date | Date of Commencement | Due date of completion | Extended date of completion | Expected date of completion | Actual Expenditure -Amount released to th contractor (Cr) | Current Progress in Detail as on 28.07.2020 | Planned | Achieved | Compliance
KIIFB PROJECTS - SCDD DEPARTMENT WORKS
1 | SCD002-02-02 | SCDD - Construction of Govt. ITI at Attipra in Thiruvananthapuram District | Trivandrum | 401 | G.O.(Rt)No. 1741/16/SCSTDD dt. 08.11.2016 Rs.700 lakhs | RMTVPM/2017-2018/2017/8155 dt.21.02.2018 Rs.230 Lakhs | 2.1 | M/s. Heather Infrastructure Pvt. Ltd. | 12 | 02.07.2018 | 18.09.2018 | 01.07.2019 | 27.12.2019 |  | 0.37 | Work completed | 100% | 100% | 100% | 0.94 | 48% | Smt.Rema P.K. General Manager in charge-EKM Ph-9497186255 | Ms.Geetha Regional Manager -TVM Ph- 8547912529 | 3rd and part bill on 22.01.2020 | _
2 | SCD002-02-05 | SCDD - Construction of Staff quarters (Type II) at Mannanthala in Thiruvananthapuram District | Trivandrum | 600 | G.O.(Rt)No. 1741/16/SCSTDD dt. 08.11.2016 Rs.300 lakhs | RMTVPM/2017-2018/2017/8218 dt.21.02.2018 Rs.172.38 Lakhs | 1.58 |  | 12 | _ | _ | _ | _ |  |  | Revised Estimate to be submitted to KIIFB for revised sanction | _ | _ | _ | _ | _ | Smt.Rema P.K. General Manager in charge -EKM Ph-9497186255 | Ms.Geetha Regional Manager -TVM Ph- 8547912529 | _ | _
3 | SCD002-16-01 | SCDD - Construction of Model Residential School and Staff quarters at Thonnakkal in Thiruvananthapuram District | Trivandrum | 5991 | G.O.(Rt)No. 1563/16/SCSTDD dt. 21.10.2016 Rs.2500 lakhs |  | _ | _ | _ |  | _ | _ | _ |  |  | TS issued. Work tendered | _ | _ | _ | _ | _ | Smt.Rema P.K. General Manager in charge-EKM Ph-9497186255 | Ms.Geetha Regional Manager -TVM Ph- 8547912529 | _ | _
4 | SCD002-02-01 | SCDD - Construction of New Building for Government ITI at Vettikavala in Kollam District | Kollam | 461 | G.O.(Rt)No. 1741/16/SCSTDD dt. 08.11.2016 Rs.700 lakhs | RMALP/2017-2018/2017/8197 dt.21.02.2018 Rs.134.9 Lakhs | 1.259 | Shri. Ansarudeen.I | 12 | 30.05.18 | 30.05.18 | 29.05.19 | 22.11.2019 |  | 0.64 | Work completed | 100% | 100% | _ | 0.66 | 59 | Smt.Rema P.K. General Manager in charge -EKM Ph-9497186255 | RAKESH C, REGIONAL MANAGER 9447133269 | 2nd and part bill on 17.12.2019 | -
5 | SCD002-04-08 | SCDD-Construction of Post-Metric Hostel for Boys at Aluva in Ernakulam District | Ernakulam | 1224 | G.O.(Rt)No. 1563/16/SCSTDD dt. 21.10.2016 Rs.500 lakhs | RMEKM/2017-2018/2017/8409 dt.21.02.2018 Rs.446.1 Lakhs | 3.47 | Ashraf.T.A Athandakkala (H) Chengera, Pattimattom P.O., Ernakulam | 12 | 30.08.18 | 30.08.18 | 29.08.19 | 31.08.2020 | 31.08.2020 | 1.56 | Interior Painting completed and Exterior painting in progress.Drainage work in progress. | 90% | 90% | 50% | 1.43 | 41 | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Beena Nair (Regional Manager) 9633540657 | 3rd and part bill on 06.04.2020 | _
6 | SCD002-07-01 | KIIFB-SCDD - Construction of New Building for ITI at Ponnani in Malappuram district | Malappuram |  | G.O.(Rt)No. 1741/16/SCSTDD dt. 08.11.2016 Rs.700 lakhs |  | N.A | N.A | N.A |  | N.A | N.A | N.A |  |  | Original proposal was as per NCVT norms of 2016.After receiving AS, NCVT norms have changed. So revised estimate proposed for an amount of 218.7 Lakhs.RE not sanctioned so far. | N.A | N.A | N.A | _ | _ | " | Ajith Kumar V V (Regional Manager), | _ | _
7 | SCD002-04-05 | KIIFB- SCDD Construction of 60 bedded Post Metric Hostel at Kozhinjampara | Palakkad | 1961.4 | G.O.(Rt)No.1563/16/SCSTDD dt 21.102.016 Rs.500 lakhs | RMTSR/2017-2018/2017/7304 dt.15.03.2018 Rs.499.91 Lakhs | 3.85 | Sri. Mohammedkutty Haji | 12 | 18.06.2018 | 18/6/2018 | 17/6/2019 | 11.09.2019 |  | 2.35 | Completed in all respects. | 100% | 100% | 100% | 2.35 | 61 | Rema P.K. General Manager -EKM Ph-9497186255 | Ajith Kumar V V (Regional Manager), | 3rd and part bill 02.11.2019 | _
8 | _ | SCDD - Model Residential school & Quarters Chakkittapara, Kozhikode. | Kozhikode | 5782.83 | G.O.(Rt)No. 1563/16/SCSTDD dt. 21.10.2016 Rs.2500 lakhs | KSCC/MD/TS/08/2017-2018 dt 05.03.2018 Rs.1504 Lakhs | _ | _ | _ | _ | _ | _ | _ | _ | _ | Site already allotted is changed. So the estimate and design has to be changed. Preparation of drawing & estimate in progress. | _ | _ | _ | _ | _ | " | Hareesh Kumar C.K (Regional Manager) 9387941306 | _ | _
9 | SCD002-04-06 | SCDD-Construction of Hostel building for 100 plus two students at Vellachal in Kasaragod District | Kasaragod | 1819 | G.O.(Rt)No. 1563/16/SCSTDD dt. 21.10.2016 Rs.500 lakhs | RMKNR/2017-2018/2017/8400 dt.21.02.2018 Rs.500 Lakhs | 3.93 | Sri. Mohammed Harish B A, Najath House, Baladukka, Nekreje PO, Kasaragod - 671 543 | 12 |  | 13.08.2018 | 12.08.2019 | 30.05.2020 | 29.11.2020 | 1.068 | Structural work completed.Laterite Masonry completed.Plastering completed,electrification work in progress.plumbing 70% completed.painting 25% completed.joinary fittings 70%completed.water proofing completed.Tilework 70% completed. | 100% | 85% | - | 1.14 | 29 | " | " | 1st & part bill-24.08.2019 | _
10 | SCD002-08-01 | SCDD-Construction of Model Residential School, Hostel, Kitchen Block and Staff Quarters at Peringome in Thaliparamba Taluk in Kannur District | Kannur | 6691 | G.O.(Rt)No. 1563/16/SCSTDD dt. 21.10.2016 Rs.2500 lakhs | RMKNR/2018-2019/2017/8845 dt.03.04.2018 Rs.1470 Lakhs | 12.62 | M/s. Hill Track Constructions (P) Ltd., Nadavayal PO, Panamaram, Wayanad - 670 721 | 18 | p | 17.09.2018 | 16.03.2020 | 30.05.2020 | 30.11.2020 | 6.75 | School BuildingStructural work completed..Plastering work completed.Tile laying 90% completed.Al.fabrication work 60% completed.Grills 80% completed.Plumbing 70% completed.Painting 20% completed.handrail work 80% completed.Hostel Building-Structural work completed.plastering work completed.Tile work 75% completed. Grill 80% completed.Plumbing 50% completed.Handrail 60% completed. Quarters Building-Masonry work completed.Plastering work GF 65%completed,FF 65% completed.Canteen Building-Plastering work 95% completed,PCC completed,Truss work completed . | 100% | 82% | _ | 7.26 | 58 | Rema P.K. General Manager -EKM Ph-9497186255 | Sri.Roy.P.S, Regional Manager,KSCC Kannur,Ph 9447716468 | 4th & part bill 02.03.2020 | _
11 | SCD002-02-04 | Construciton of Building for Pre -Examination Training Centre at Azhikode in Kannur District | Kannur | 523.03 | G.O.(Rt)No. 1741/16/SCSTDD dt. 08.11.2016 Rs.100 lakhs | RMKNR/2017-2018/2017/7769 dt.21.02.2018 Rs.130 Lakhs | 1.0457 | Sri.O.C.Ullasan,'Sopanam',Near Kunnav temple,Ambika Road,Pallikkunnu,Kannur-670004 | 12 | 25.10.2019 | 25.10.2019 | 24.10.2020 | - | 23.01.2021 |  | G F roof slab concreting completed. Stair room roof slab centering & shuttering in progress. Terrace column work completed. | 50% | 48% | - | _ | _ | Rema P.K. General Manager -EKM Ph-9497186255 | -do- | - | -
12 | SCD002-04 | SCDD-Construction of Pre-Matric Hostel for 30boys at Kadirur in Kannur District | Kannur | 1134.3 | G.O.(Rt)No. 1563/16/SCSTDD dt. 21.10.2016 Rs.200 lakhs | RMKNR/2017-2018/2017/8829 dt.21.02.2018 Rs.200 Lakhs | 1.6 | Sri.M.Muhammed Kunji,Masthikund House,Muliyar P.O,Kasargod-671542 | 12 | 28.10.2019 | 28.10.2019 | 27.10.2020 | - | 26.01.2021 |  | F F Lintel& sunshade concreting work completed F F roof slab centering & shuttering work in progress | 30% | 27% | - | _ | _ | Rema P.K. General Manager -EKM Ph-9497186255 | Sri.Roy.P.S, Regional Manager,KSCC Kannur,Ph 9447716468 | - | -
13 | SCD002-04 | SCDD-Construction of Post-Matric Hostel for 40 Boys at Thana in Kannur District | Kannur | 1000.42 | G.O.(Rt)No. 1563/16/SCSTDD dt. 21.10.2016 Rs.500 lakhs | RMKNR/2017-2018/2017/8261 dt.21.02.2018 Rs.200 Lakhs | 1.57 | Sri.Baby Joseph,Thachilettu House,Kuniyanpuzha.P.O,Kannur-670632 | 12 | 15.10.2019 | 15.10.2019 | 14.10.2020 | - | 13.01.2021 |  | Ground floor slab concreting | 30% | 18% | - | _ | _ | Rema P.K. General Manager -EKM Ph-9497186255 | Sri.Roy.P.S, Regional Manager,KSCC Kannur,Ph 9447716468 | - | _
KIIFB Project- Progress Report as on 28.07.2020-ST Development Department Works-SPV KSCC Ltd
[17 empty] | Physical Progress (%) | Physical Progress (%) | Physical Progress (%) | Financial Progress (in Cr) | Percentage of Bill Amount Sanctioned (%) | PMU Head Name & Contact No: | Project-in-charge Name & Contact No: | Last Bill details | Tendative Date for the next bill Due
Sl No: | Project Code | Project Name | District | Buillt up Area in (m2) | A S Amount in (Lakhs) | Final T S Amount in (Lakhs) | Agreed PAC (Cr) | Name of Contractor | Duration of work (Months) | Site Hand over Date | Date of Commencement | Due date of completion | Extended date of completion | Expected date of completion | Actual Expenditure -Amount released to th contractor (Cr) | Current Progress in Detail as on 28.07.2020 | Planned | Achieved | Compliance
KIIFB PROJECTS - ST DEPARTMENT WORKS
1 | SCD003-03-01 | STDD - Model residential school at Kuttichal, Thiruvananthapuram District | Trivandrum | 10190 | G.O.(Rt)No. 1581/16/SCSTDD dt. 22.10.2016 Rs.2500 lakhs |  | _ | _ | _ |  | _ | _ | _ |  |  | TS issued. BOQ not obtained. | _ | _ | _ | _ | _ | Smt.Rema P.K. General Manager in charge-EKM Ph-9497186255 | Ms.Geetha Regional Manager -TVM Ph- 8547912529 | _ | _
2 | TRAN2-SCD-002-04 | STDD-Youth Hostel Peringamala,Palode | Trivandrum | 1158 | G.O.(Rt)No. 1581/16/SCSTDD dt. 22.10.2016 Rs.500 lakhs |  | _ | _ | _ |  | _ | _ | _ |  |  | Revised site location details recieved from STDD. AR drawing also has to be revised as the original plan cannot be accomadated in the new site. Revision of drawing in progress | _ | _ | 35% | 0.64 | 17 | Smt.Rema P.K. General Manager in charge -EKM Ph-9497186255 | RAKESH C, REGIONAL MANAGER 9447133269 | 1st and part bill on 12.11.2019 | -
3 | SCD002-04-01 | STDD-Construction of 100 bedded Pre-Matric Hostel for Girls at Achankovil in Kollam District | Kollam | 1348 | G.O.(Rt)No. 1581/2016/SCSTDD Dated 22.10.2016 Rs.500 Lakhs | RMALP/2017-2018/2017/8482 dt.21.02.2018 Rs.471 lakhs | 3.79 | Sri. Surendran Pillai | 12 | 05.07.2018 | 05.07.2018 | 04.07.2019 | 06.07.2020 | 06.07.2020 | 0.641 | Construction of Counterfort retaining wall in the back side is completed. Front side retaining wall completed .lift shear wall completed. column concreting upto Ground floor level completed.Solid block masonry upto lintel level completed. Lintel works completed.Slopping sunshade beam concreting completed. Shuttering of groud floor roof and staircase works going on.The proposed site is hotspot area. So the work is going on with limited labour and materials available at site. | 65% | 35%
4 | SCD002-04 | KIIFB - STDD - Construction of New hostel building for boys at Nadukani in Idukki District. | Idukki | 1304 | G.O.(Rt)No. 1581/16/SCSTDD dt. 22.10.2016 Rs.500 lakhs | RMKTM/2017-2018/2017/8234 dt.21.02.2018 Rs.342 lakhs | 2.81 | Sri.Tellus Stephen, Kizhakkumthala House, Mullapuzhachal P.O, Vazhakkulam-686670 | 12 | 18.05.2018 | 18.05.18 | 17.05.19 | 31.03.2020. | 30.06.2020 | 0.87 | Building work almost completed, road work not yet started. | 98% | 95% | 96.9% | 8717754/- | 31.08% | Smt.Rema P.K. General Manager in charge -EKM Ph-9497186255S | Sri. Riyad, Regional Manager, Kottayam 9447096155 | 1st and part bill on16.12.2019
5 | SCD002-02 | KIIFB -STDD - Construction of New Academic block building for Vocational Training Centre at Nadukani in Idukki District. | Idukki | 1585.65 | G.O.(Rt)No. 1581/16/SCSTDD dt. 22.10.2016 Rs.1000 lakhs | RMKTM/2017-2018/2017/8881 dt.27.03.2018 Rs.403 lakhs | 3.29 | Sri. Ramesh Babu, Swathy Constructions, Karthika, Karumpady, Muvattupuzha. | 12 | 16.05.2018 | 15.05.18 | 14.05.19 | 15.03.2020 |  | 1.89 | Civil Work completed, electrical work ongoing | 100% | Civil Work -100% Electrical-85% | 2% | 18629822/- | 56.6% | ,, | ,, | 2nd and part bill on 17.03.2020
6 | SCD002-04-02 | KIIFB -STDD - Construction of Hostel building for Boys at Kodalippara in Idukki District. | Idukki | 1309.14 | G.O.(Rt)No. 1581/16/SCSTDD dt. 22.10.2016 Rs.500 lakhs | RMKTM/2017-2018/2017/8828 dt.27.03.2018 Rs.391 lakhs | 3.24 | Sri. E.M. Madhu, Eettical (H), Poonjar(S) P.O, Kottayam. | 12 | 21.05.2018 | 21.05.18 | 20.05.19 | 20.03.2020 | 31.07.2020 | 1.49 | Completed | 100% | 95% | 4% | 14971753/- | 39.69% | ,, | ,,
7 | SCD002-04 -07 | STDD-Construction of Post-Metric Hostel for Girls at Neriyamangalam in Ernakulam District | Ernakulam | 1730 | G.O.(Rt)No. 1581/16/SCSTDD dt. 22.10.2016 Rs.500 lakhs | RMEKM/2017-2018/2017/8163 dt.21.02.2018 Rs.454.75 lakhs | 3.74 | Sri.Bindhu Sudhakaran,M/s Vilakkumadom Construction,Srikailas,Pravachambalam,Nemam P.O,Thiruvananthapuram | 12 | 20.02.2019 | 20.02.2019 | 19.02.2020 | _ |  |  | Site handed over to the contractor on 20.02.2019. Setting out works were started on 26.04.2019. But Due to the objection from local people the work not started till date.As per the meeting held on 23.10.2019 in the presence of Hon’ble MLA Sri Antony John proposal for a new site location is suggested. The work could not be started as the site was changed by STDD. The construction in the new site require in principal approval from KIIFB along with approval for carrying out architectural drawing , soil investigation and structural design work in the new location. | _ | _ | _ | _ | _ | " | Beena Nair (Regional Manager) 9633540657 | _ | _
8 | _ | STDD-Construction of Pre-Metric Hostel for Boys at Pinavoorkudi in Ernakulam District | Ernakulam | 1566.46 | G.O.(Rt)No. 1581/16/SCSTDD dt. 22.11.2016 Rs.500 lakhs |  | Work not tendered. | _ | 12 |  | _ | _ | _ |  |  | The site for the proposed construction was changed thrice by the STDD. The project is approved as per Order No. SCD002-09-PA-02 Dated 20.09.2019 of Chief Executive Officer, KIIFB Estimate is prepared based on DSR 2016 by adding cost index @ 46.08%. Total estimate amount comes to Rs.4,03,00,000/- for which FS obtained for Rs. 3,92,00,000/- later cost index changed from 46.08% to 39.89% and GST 12% included. In this context revised estimate for the work is necessary. After recalculating estimate amount comes to Rs. 421,05,766.91. Hence revised sanction is to be obtained from KIIFB . TS committee approval is obtained for the proposal on 13.03.2020. Now the same has to be submitted to KIIFB for revised Financial Sanction. | _ | _ | _ | _ | _ | " | Beena Nair (Regional Manager) 9633540657 | _ | _
9 | SCD002-04 -15 | Construction of Pre-Matric Hostel for 100 Boys at Kuttikkol in Kasaragod District | Kasaragod | 1832 | G.O.(Rt)No. 1581/16/SCSTDD dt. 22.10.2016 Rs.500 lakhs | RMKNR/2017-2018/2017/8166 dt.21.02.2018 Rs.420 lakhs | 3.27 | Sri. C.L Abdulla, PWD Contractor, C.L House, Kizhur, Chandragiri PO, Kasaragod - 671 317 | 12 | 05.10.2018 | 05.10.2018 | 04.10.2019 | 31.03.2020 | 31.07.2020 | 1.079 | Plastering work completed.Flooring 95% completed. Painting 95% completed.Plumbing completed.handrail fixing completed.water proofing 100%completed.sanittary fiittings 70% completed. | - | 90% | - | 1.15 | 35 | Rema P.K. General Manager -EKM Ph-9497186255 | Sri.Roy.P.S, Regional Manager,KSCC Kannur,Ph 9447716468 | 1st & part bill 17.09.2019 | _
10 | SCD002-04-09 | Construction of Pre-Matric Hostel for 100 girls at Bedadukka in Kasaragod District | Kasaragod | 1832 | G.O.(Rt)No. 1581/16/ SCSTDD dt. 22.10.2016 Rs.500 lakhs | RMKNR/2017-2018/2017/8228 dt.21.02.2018 Rs.470 lakhs | 3.697 | Sri. C.L Abdulla, PWD Contractor, C.L House, Kizhur, Chandragiri PO, Kasaragod - 671 317 | 12 | 05.10.2018 | 05.10.2018 | 04.10.2019 | 31.03.2020 | 31.07.2020 | 1.38 | Plumbing work & sanittary 80% completed.Painting completed.Flooring completed.handrail fixing completed. Watchman cabin work in finishing stage | 100% | 95% | - | 1.47 | 40 | " | " | 1st & part bill -16.09.2019 | _
11 | SCD003-04 | Construction of Model Residential School, Hostel, Kitchen Block and Staff Quarters at Aralam in Kannur District | Kannur | 9033 | G.O.(Rt)No. 1581/16/SCSTDD dt. 22.10.2016 Rs.2500 lakhs | RMKNR/2018-2019/2017/8915 dt.03.04.2018 Rs.1860 lakhs | 15.88 | M/s. Hill Track Constructions (P) Ltd., Nadavayal PO, Panamaram, Wayanad - 670 721 | 18 | 02.11.2018 | 02.11.2018 | 01.05.2020 | 01.11.2020 | 01.11.2020 | 1.98 | Boundary compound wall400 mtr Compound wall Completd( 800 mtr is to be done).School BuildingStructural work 100% Completed, School building - GF- Masonry, Plastering , Floor PCC , Window Grill Work Completed, Door Frame,plumbing work Completed. FF – Masonry , Plastering work,door frame &shutter Completed. External plastering completed.External plumbing work in progress. Quarters Building-GF column completed.G.F Slab concreing 50%complated. Balance 50% centering &shuttering work in progress.-Boys hostel- Ground Floor Masonry, Plastering , Floor PCC Door Frame work 95% Completd.first Floor- door frame & plastering work 90% completed.External plumbing work in progress.Extenal primer 90% completed. Girls hostel- structural work,masonry work completed.Gf-plastering,floor PCC & door frame work 95 % completed.Ff-door frame work completed.Inside Plastering 90% completed.External plastering80% completed. | 100% | 72% | - | 5.8 | 36 | Rema P.K. General Manager -EKM Ph-9497186255 | -do- | 3rd& part bill 09.03.2020 | _