## scst
KSCC BIWEEKLY PROGRESS REPORT 30/09/2020
Sl No: | SPV | Project Code | Project Name | Sub-Project Name | Package Name/Package code | District | Accepted Tender Amount (Cr) | Name of Contractor | Duration of work (Months) | Date of Commencement | Due date of completion | Extended date of completion | Current Progress in Detail | Physical Progress (%) |  |  | Financial Progress (in Cr) | Percentage of Bill Amount Sanctioned (%) | PMU Head Name & Contact No: | Project-in-charge Name & Contact No: | Last Bill details | Tendative Date for the next bill Due
[14 empty] | Planned | Achieved | Compliance
1 | KSCC | SCD002-02 | Construction of ITI and other buildings at various locations (5 numbers) | SCDD - Construction of New Building for Government ITI at Vettikavala in Kollam District | SCD002-02-01 | Kollam | 1.112 | Shri. Ansarudeen.I | 12 | 30.05.18 | 29.05.19 | 22.11.2019 | Completed | 100% | 100% |  | 9907647 | 85% |  | RAKESH C, (RM) 9447133269 | 3rd and part bill submitted. | october
2 | KSCC |  |  | Electrification of New Building for Government ITI at Vettikavala in Kollam District | SCD002-02-07 | Kollam | 0.147 | AnilKumar, Ambady Electricals | 3 | 13.09.2019 | 12.12.2019 | 10.12.2019 | Completed |  |  |  | 0.0748 | 0 |  |  | 23.05.2020 | 30.09.2020
3 | KSCC |  |  | SCDD - Construction of Govt. ITI at Attipra in Thiruvananthapuram District | SCD002-02-02 | Thiruvananthapuram | 1.96 | M/s. Heather Infrastructure Pvt. Ltd. | 12 | 18.09.2018 | 01.07.2019 | 27.12.2019 | Completed | 100% | 100 |  | 1.3 | 48% | Rema.P.K(GM) 9497186255 | Geetha .A.V(RM)8547912529 | 3rd and part bill dtd 16.12.2019 | 4th and final bill will be submitted soon
4 | KSCC |  |  | Electrification of New Block for ITI at Attipra in Thiruvananthapuram District | SCD002-02-08 | Thiruvananthapuram | 0.1429 | K.Pradeep, Mithun Electricals | 3 | 12.09.2019 | 11.12.2019 | 11.12.2019 | Completed |  |  |  | 0.108 | 0 |  |  | 29.02.2020 | 30.09.2020
5 | KSCC |  |  | KIIFB -STDD - Construction of New Academic block building for Vocational Training Centre at Nadukani in Idukki District. | SCD002-02-03 | Idukki | 3.29 | Sri. Ramesh Babu, Swathy Constructions, Karthika, Karumpady, Muvattupuzha. | 12 months | 15.05.18 | 14.05.19 | 31.05.2020 | Work completed | 100% | 100% | 0 | 2.53 | 76 | Rema.P.K(GM) 9497186255 | Sunil.M.Roy 9400783789 | CC IIIrd & Part bill on 30.06.2020 | RE submitted for sanction.
6 | KSCC |  |  | Electrification of New Academic Block Building for Boys for VTC Nadukani in Idukki District | SCD002-02-06 | Idukki | 0.2546 | Shylaja, Linsta Services | 6 | 10.10.2019 | 09.04.2020 | 09.10.2020 | 95% | 1 | 95% | [6 empty] | 15.08.2020
7 | KSCC |  |  | Construciton of Building for Pre -Examination Training Centre at Azhikode in Kannur District | SCD002-02-04 | Kannur | 1.046 | Sri.O.C.Ullasan,'Sopanam',Near Kunnav temple,Ambika Road,Pallikkunnu,Kannur-670004 | 12months | 25.10.2019 | 24.10.2020 | _ | Stair room roof slab concreting completed.Terrace column concreting completed.P.C.C work 60% completed | 60% | 58% | 52% | 0.6 | _ | Rema.P.K(GM) 9497186255 | Sri. Roy. P.S,Regional Manager, KSCC, Kannur,9447716468 | 2nd &part bill sent on 25.08.2020
8 | KSCC |  |  | SCDD - Construction of Staff quarters (Type II) at Mannanthala in Thiruvananthapuram District | SCD002-02-05 | Thiruvananthapuram | - | - | 12 | - | - | - | Revised Estimate submitted to KIIFB for revised TS | [5 empty] | Rema.P.K(GM) 9497186255 | Geetha .A.V(RM)8547912529
9 | KSCC | SCD002-03 | Construction of Model Residential School At Kozhikod Chakkittappara | Construction of Model Residential School At Kozhikod Chakkittappara | _ | Kozhikode | [6 empty] | site already allotted is changed. So the estimate and design has to be changed. Preparation of drawing & estimate in progress. | [5 empty] | Rema.P.K(GM) 9497186255 | Ajith Kumar V V (RM), 8281882156
10 | KSCC | SCD002-04 | Construction of hostels at various locations (13 numbers) | STDD - Construction of 100 bedded Pre Matric Hostel for girls at Achankovil in Kollam District - Civil works | SCD002-04-01 | Kollam | 3.79 | Shri. S.Surendran Pillai | 12 | 05.07.18 | 04.07.19 | 05.07.2020 | First floor column works going on | 72% | 45% |  | 0.64 | 17% | Rema.P.K(GM) 9497186255 | RAKESH C, RM 9447133269 | 1st and part bill sanctioned | october first week
11 | KSCC |  |  | STDD - Construction of Post Matric hostel for Boys at Kodalippara in Idukki District - Civil works | SCD002-04-02 | Idukki | 3.24 | Sri. E.M. Madhu, Eettical (H), Poonjar(S) P.O, Kottayam. | 12 months | 21.05.18 | 20.05.19 | 30.06.2020 | Work completed. | 100 | 100 | 0 | 1.49 | 45 | Smt.Rema P.K. General Manager in charge -EKM Ph-9497186255 | Mahin Aboobackar 9496335515 | CC IInd& Part bill on 14.02.2020 | 03.09.2020
12 | KSCC |  |  | Electrification of Post Metric Hostel for Boys at Kodalippara in Idukki District | SCD002-04-21 | Idukki | 0.1189 | A.R.Sivasankaran Varappetty | 6 | 18.11.2019 | 17.05.2020 | 17.07.2020 | Completed |  |  |  | 0.12217 |  |  |  | 24.08.2020 | 24.10.2020
13 | KSCC |  |  | STDD - Construction of New hostel building for Boys at Nadukani in Idukki District - Civil works | SCD002-04-03 | Idukki | 2.8 | Sri.Tellus Stephene Kizhakkumthala House Mullapuzhalkkal P.O Vazhakkulam - 686670 | 12 months | 18.05.18 | 17.05.19 | 30.06.2020 | Work Completed. | 100 | 100 | 0 | 0.87 | 31 | Smt.Rema P.K. General Manager in charge -EKM Ph-9497186255 | Sunil.M.Roy 9400783789 | CC 1st& Part bill on 06.12.2019 | 07.09.2020
14 | KSCC |  |  | Electrification of New hostel building for Boys at Nadukani in Idukki District | SCD002-04-16 | Idukki | 0.1331 | A.R.Sivasankaran Varappetty | 6 | 10.10.2019 | 09.04.2020 | 29.09.2020 | Completed | [8 empty] | 30.09.2020
15 | KSCC |  |  | STDD - Construction of Pre Matric Hostel for 100 Boys at Kuttikkol in Kasargode District | SCD002-04-04 | Kasargode | 3.27 | Sri.C.L. Abdulla, C.L House, Kizhur, Chandragiri PO, Kasaragod 671 317 | 12months | 05.10.2018 | 04.10.2019 | 31.07.2020 | Plumbing &sanittary fiittings 80% completed.Painting work completed | 100% | 99% | 99% | 3.87 | 78% | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Sri. Roy. P.S,Regional Manager, KSCC, Kannur,9447716468 | 3rd part bill under preparation | 30.10.2020
16 | KSCC |  |  | Electrification of Pre-Matric Hostel for 100 Boys at Kuttikkol in Kasargod District | SCD002-04-15 | Kasargode | 0.1237 | Spands Electrcial Contractors | 6 | 05.10.2019 | 04.04.2020 | 04.10.2020 | 85% | 0.95 | 0.84 | [6 empty] | 30.09.2020
17 | KSCC |  |  | SCDD - Construction of 60 bedded Post Metric Hostel at Kozhinjampara in Palakkad District | SCD002-04-05 | Palakkad | 3.85 | Sri M Ahammedkutty Haji |  | 18/06/2018 | 17/06/2019 | #### | Work completed | 100% | 100% | 100% | 3.65 | 95% | Rema.P.K(GM) 9497186255 | K. Radhamany No-9605600308 | CC THIRD AND PART BILL RS. 2.29 CRORE DATED-02.11.2019 | Final bill under preperation.
18 | KSCC |  |  | Electrification of 60 bedded Post Metric Hostel at Kozhinjampara in Palakkad District | SCD002-04-17 | Palakkad | 0.1309 | SunilKumar, Universal Electric Company | 3 | 18.09.2019 | 17.12.2019 | 17.11.2019 | Completed |  |  |  | 0.09232 | 0 |  |  | 21.12.2019 | 15.09.2020
19 | KSCC |  |  | SCDD - Construction of Hostel building for 100 plus two students at Vellachal in Kasaragod District - Civil works | SCD002-04-06 | Kasargode | 3.93 | Sri. Muhammed Harish. B.A, Najath (H), Baladkka, Kasaragod | 12months | 13.08.2018 | 12.08.2019 | 31.08.2020 | Structural work completed. Laterite Masonry completed. Plastering completed, electrification work in progress. plumbing 95% completed. painting 80% completed. joinary fittings 80%completed. water proofing completed.Tilework 95% completed.Handrail fixing completed.Yard levelling in progress.Septic Tank 70% completed.Truss work 70% completed. | 100% | 88% | 75% | 3 | 37% | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Sri. Roy. P.S,Regional Manager, KSCC, Kannur,9447716468 | 2 nd & part bill sent on 11.08.2020
20 | KSCC |  |  | Electrification of Hostel building for 100 plus two students at Vellachal in Kasargode District | SCD002-04-13 | Kasargode | 0.1248 | Vinod Kumar, City Electricals | 6 | 16.09.2019 | 15.03.2020 | 15.10.2020 | 50% | 0.9 | 0.55 | [6 empty] | 30.09.2020
21 | KSCC |  |  | STDD - Construction of Post- Metric Hostel for Girls at Neriyamangalam in Ernakulam District - Civil works | SCD002-04-07 | Ernakulam |  |  | Site handed over to the contractor on 20.02.2019. Setting out works were started on 26.04.2019. But Due to the objection from local people the work not started till date.As per the meeting held on 23.10.2019 in the presence of Hon’ble MLA Sri Antony John proposal for a new site location is suggested. The work could not be started as the site was changed by STDD. the arranged work was cancelled and the contract terminated.The construction in the new site require in principle approval from KIIFB along with approval for carrying out architectural drawing , soil investigation and structural design work in the new location. | [9 empty] | Rema.P.K(GM) 9497186255 | Rakesh C,(i/c)RMEKM,KSCC Ph No-9447133269
22 | KSCC |  |  | SCDD - Construction of Post - Metric Hostel for Boys at Aluva in Ernakulam District - Civil works | SCD002-04-08 | Ernakulam | 3.4724 | Civil - Shri Ashraf T A | 12 | 30.08.2018 | 29.08.2019 | 31.08.2020 | Interior Painting works completed and Exterior painting works in Ground floor in progress.Drainage work Completd and slab completed. | 95 | 90 | 94.74 | 1.57 | 45.2 | Rema.P.K(GM) 9497186255 | Rakesh C,(i/c)RMEKM,KSCC Ph No-9447133269
23 | KSCC |  |  | Electrification of Post Metric Hostel for Boys at Aluva in Ernakulam District | SCD002-04-12 | Ernakulam | 0.1172 | Biju Jose, Metro Contracting | 6 | 11.11.2019 | 10.5.2020 | 10.9.2020 | Completed | [8 empty] | 15.09.2020
24 | KSCC |  |  | STDD - Construction of Pre-Matric Hostel for 100 girls at Bedadukka in Kasaragod District - Civil works | SCD002-04-09 | Kasargode | 3.69 | Sri.C.L. Abdulla, C.L House, Kizhur, Chandragiri PO, Kasaragod 671 317 | 12months | 05.10.2018 | 04.10.2019 | 31.12.2020 | Plumbing work & sanittary 80% completed.Painting completed.Flooring completed.handrail fixing completed.Watchman cabin work in finishing stage | 100% | 99% | 99% | 4.45 | 69% | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Sri. Roy. P.S,Regional Manager, KSCC, Kannur,9447716468 | 3rd & part bill under preparation | 30.10.2020
25 | KSCC |  |  | Electrification of Pre-Matric Hostel for 100 girls at Bedadukka in Kasargod District | SCD002-04-14 | Kasargode | 0.1255 | Spands Electrcial Contractors | 6 | 15.09.2019 | 14.03.2020 | 14.10.2020 | 95% | 1 | 0.95 |  | 0.06922 | 0 |  |  | 21.12.2019 | 30.09.2020
26 | KSCC |  |  | SCDD -Construction of Post-Matric Hostel at Thana in Kannur District - Civil works | SCD002-04-10 | Kannur | 1.57 | Sri.Baby Joseph,Thachilettu House,Kuniyanpuzha.P.O,Kannur-670632 | 12months | 15.10.2019 | 14.10.2020 | _ | Ground floor slab concreting 50% completed.FF Column work started.GF masonry work started. | 30% | 18% | 18% | 0.33 | _ | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Sri. Roy. P.S,Regional Manager, KSCC, Kannur,9447716468 | 1st part bill under preparation | 30.10.2020
27 | KSCC |  |  | SCDD - Construction of Pre-Matric Hostel for 30 boys at Kathirur in Kannur District - Civil works | SCD002-04-11 | Kannur | 1.637 | Sri.M.Muhammed Kunji,Masthikund House,Muliyar P.O,Kasargod-671542 | 12months | 28.10.2019 | 27.10.2020 | _ | Second floor roof slab concreting in progress.GF&FF Masonry work in progress.GF plastering started. | 45% | 42% | 42% | 0.68 | _ | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Sri. Roy. P.S,Regional Manager, KSCC, Kannur,9447716468 | 1st part bill under preparation | 30.10.2020
28 | KSCC |  |  | STDD-Youth Hostel Peringamala,Palode | _ | Thiruvananthapuram | - | - | - | - | - | - | Revised site location details recieved from STDD on 21.01.2020 only and AR drawing also has to be revised as the original plan cannot be accomadated in the new site. | [5 empty] | Rema.P.K(GM) 9497186255 | Geetha .A.V(RM)8547912529
29 | KSCC | SCD002-08 | Construction of Model Residential School at Thaliparamba, Kannur | SCDD -Construction of Model Residential School, Hostel, Staff Quarters and canteen block at Peringome in Thaliparamba in Kannur District - Civil works | SCD002-08-01 | Kannur | 12.62 | M/s. Hill Track Constructions (P) Ltd., Nadavayal PO, Panamaram, Wayanad - 670 721 | 18months | 17.09.2018 | 16.03.2020 | 31.08.2020 | School Building- Structural work completed. Plastering work completed. Tile laying completed. Al.fabrication work 75% completed. Grills 85% completed. Plumbing 95% completed. Painting 50% completed. handrail work completed. Hostel Building- Structural work completed. plastering work completed. Tile work 85% completed. Grill 80% completed. Plumbing 90% completed. Handrail completed.Painting 70% completed .doors &windows 70%completed.Quarters Building- Laterite work for wall completed. Plastering work completed.pumbing 90% competed.door shutter 70%completed.window shutter fixing started.Painting 20% competed.. Canteen Building- Plastering work completed, PCC completed, Truss work completed.Tilework completed.door shutter fixing competed.Plumbing 90%completed.False ceiing completed.Painting 50%completed. | 100% | 80% | 65% | 10.47 | 58% | Rema.P.K(GM) 9497186255 | Sri. Roy. P.S,Regional Manager, KSCC, Kannur,9447716468 | 5th bill sent on 14.09.2020
30 | KSCC |  |  | Electrification of Model Residential School at Peringome in Kannur District | SCD002-08-02 | Kannur | 0.6196 | S.Suresh, Meco Electricals, Thamarasserry | 12 | 21.11.2019 | 20.11.2020 | 20.11.2020 | 0.8 | 0.8 | 1 |  | 0.352 |  |  |  | 14.09.2020 | 05.12.2020
31 | KSCC | SCD002-09 | STDD - Construction of Pre-Metric Hostel for 100 Boys at Pinavoorkudi in Ernakulam District | _ | _ | Ernakulam |  | The site for the proposed construction was changed thrice due to various reason. The project was approved as per Order No. SCD002-09-PA-02 Dated 20.09.2019 of Chief Executive Officer, KIIFB Estimate was prepared based on DSR 2016 by adding cost index @ 46.08%. Total estimate amount came to Rs.4,03,00,000/- for which FS obtained for Rs. 3,92,00,000/- Later cost index changed from 46.08% to 39.89% and GST 12% included,and also suggestions were put forward byKIIFB for making those changes in estimate. In this context estimate has been revised. After recalculating estimate amount comes to Rs.3,91,95,826.27.prepared based on DSR 2016 by adding cost index @ 46.08%. Total estimate amount came to Rs.4,03,00,000/- for which FS obtained for Rs. 3,92,00,000/- Later cost index changed from 46.08% to 39.89% and GST 12% included,and also suggestions were put forward byKIIFB for making those changes in estimate. In this context estimate has been revised. After recalculating estimate amount comes to Rs.3,91,95,826.27. | [10 empty] | Rema.P.K(GM) 9497186255 | Rakesh C,(i/c)RMEKM,KSCC Ph No-9447133269
32 | KSCC | SCD002-16 | Construction of MRS at Thonnakkal, Thiruvananthapuram | Construction of Model Residential School at Thonnakkal in Thiruvananthapuram District | SCD002-16-01 | Thiruvananthapuram | - | - | 24 | - | - | - | TS issued. Work tendered | [5 empty] | Rema.P.K(GM) 9497186255 | Geetha .A.V(RM)8547912529
33 | KSCC | SCD003-03 | Construction of Building for MRS Kuttichal | Construction of Model Residential School at Kuttichal in Thiruvananthapuram District | SCD003-03-01 | Thiruvananthapuram | - | - | 24 | - | - | - | TS issued. Work to be tendered. | [5 empty] | Rema.P.K(GM) 9497186255 | Geetha .A.V(RM)8547912529
34 | KSCC | SCD003-04 | Construction of Model Residential School at Aralam, Kannur | STDD - Construction of Model Residential School, Hostels, canteen and Staff Quarters at Aralam in Kannur District - Civil works | SCD003-04-01 | Kannur | 15.88 | M/s. Hill Track Constructions (P) Ltd., Nadavayal PO, Panamaram, Wayanad - 670 721 | 18months | 02.11.2018 | 01.05.2020 | 01.11.2020 | Boundary compound wall 400 mtr Completed.School building- Structure completed .Walls and plastering work completed. Flooring completed except stairs. Toilet block- GF &FF Tile works completed .Doors and safety grills completed ,Septic tanks completed,External &internal primer work almost completed. external plumbing works almost completed.Aluminium window shutters completed.Stair handrail work 80% completed.Ramp flooring completed.Septic tank&soakpit completed. Staff Quarters-GF column completed.G.F Slab concreting completed.FF column completed.FF Slab concreting completed Second floor column work in progress.GF masonry work started. Boys hostel- Structure completed. Walls completed ,Plastering completed. Flooring completed except stair .Stair handrail 75%completed. Doors and safety grills completed.GF toilets- Tiles and Plumbing works completed,FF toilets plumbing completed,tilework almost completed. Primer work interior and exterior 95% completed .Aluminium window shutters FFcompleted.External plumbing almost completed.Septic tank &soakpit completed .Girls hostel- Structure completed, Laterite work completed, Plastering completed, Doors completed.window grill 90% completed.Toilet blocks at GF- tile and plumbing works completed.flooring except verandha and stair completed.External plumbing work 80%completed.Stair handrail 75%completed. Primer 70% completed.Aluminium window shutters FF in progress.Septic Tank &soakpit completed. | 100% | 80% | 60% | 12.7 | 48% | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Sri. Roy. P.S,Regional Manager, KSCC, Kannur,9447716468 | 5th& part bill under preparation | 15.10.2020
35 | KSCC |  |  | Electrification of Model Residential School at Aralam in Kannur District | SCD003-04-02 | Kannur | 0.6837 | Sivaram, Jayanthi Electricals | 12 | 11.11.2019 | 10.11.2020 | 10.01.2020 | 70% | 0.85 | 0.87 | [6 empty] | 10.10.2020
36 | KSCC | SCD002-07 | Construction of Post Matric Hostel for ICSETS & PETC students at Mannanthala Thiruvananthapuram, Construction of Staff Quarters for Officers, Building construction of ITI Attippra & Ponnani at Malappuram | Construction of New Building for ITI at Ponnani in Malappuram District | SCD002-07-01 | Malappuram | Original proposal was as per NCVT norms of 2016.After receiving AS NCVT norms are changed.So revised estimate proposed for an amount of 218.7 Lakhs.RE not sanctioned so far. | [11 empty] | Rema.P.K(GM) 9497186255