## 31.10.2020
KSCC BIWEEKLY PROGRESS REPORT 31/10/2020
Sl No: | SPV | Project Code | Project Name | Sub-Project Name | Package Name/Package code | District | Accepted Tender Amount (Cr) | Name of Contractor | Duration of work (Months) | Date of Commencement | Due date of completion | Extended date of completion | Current Progress in Detail | Physical Progress (%) |  |  | Financial Progress (in Cr) | Percentage of Bill Amount Sanctioned (%) | PMU Head Name & Contact No: | Project-in-charge Name & Contact No: | Last Bill details | Tendative Date for the next bill Due
[14 empty] | Planned | Achieved | Compliance
1 | KSCC | SCD002-02 | Construction of ITI and other buildings at various locations (5 numbers) | SCDD - Construction of New Building for Government ITI at Vettikavala in Kollam District | SCD002-02-01 | Kollam | 1.112 | Shri. Ansarudeen.I | 12 | 30.05.18 | 29.05.19 | 22.11.2019 | completed | 100% | 100% |  | 9907647 | 0.85 |  | RAKESH C, (RM) 9447133269 | 3rd and part bill sanctioned and submitted to KIIFB for payment on 09.07.2020 | october
2 | KSCC |  |  | Electrification of New Building for Government ITI at Vettikavala in Kollam District | SCD002-02-07 | Kollam | 0.147 | AnilKumar, Ambady Electricals | 3 | 13.09.2019 | 12.12.2019 | 10.12.2019 | Complete | 100% | 100% | 100% | 0.0748 | 0 |  |  | 23.05.2020 | 30.09.2020
3 | KSCC |  |  | SCDD - Construction of Govt. ITI at Attipra in Thiruvananthapuram District | SCD002-02-02 | Thiruvananthapuram | 1.96 | M/s. Heather Infrastructure Pvt. Ltd. | 12 | 18.09.2018 | 01.07.2019 | 27.12.2019 | Completed | 100% | 100% |  | 1.3 | 48% | Rema.P.K(GM) 9497186255 | Geetha .A.V(RM)8547912529 | 3rd and part bill dtd 16.12.2019 | 4th and final bill will be submitted soon
4 | KSCC |  |  | Electrification of New Block for ITI at Attipra in Thiruvananthapuram District | SCD002-02-08 | Thiruvananthapuram | 0.1429 | K.Pradeep, Mithun Electricals | 3 | 12.09.2019 | 11.12.2019 | 11.12.2019 | Complete | 100% | 100% | 100% | 10.8% | 0% |  |  | 29.02.2020 | 30.09.2020
5 | KSCC |  |  | KIIFB -STDD - Construction of New Academic block building for Vocational Training Centre at Nadukani in Idukki District. | SCD002-02-03 | Idukki | 3.29 | Sri. Ramesh Babu, Swathy Constructions, Karthika, Karumpady, Muvattupuzha. | 12 months | 15.05.18 | 14.05.19 | 30.06.2020 | Work completed | 100 | 100 | 0 | 2.53 | 76 | Rema.P.K(GM) 9497186255 | Sunil.M.Roy 9400783789 | CC IIIrd & Part bill on 30.06.2020 | RE submitted for sanction.
6 | KSCC |  |  | Electrification of New Academic Block Building for Boys for VTC Nadukani in Idukki District | SCD002-02-06 | Idukki | 0.2546 | Shylaja, Linsta Services | 6 | 10.10.2019 | 09.04.2020 | 09.11.2020 | 95% | 100% | 95% | [6 empty] | 15.08.2020
7 | KSCC |  |  | Construciton of Building for Pre -Examination Training Centre at Azhikode in Kannur District | SCD002-02-04 | Kannur | 1.046 | Sri.O.C.Ullasan,'Sopanam',Near Kunnav temple,Ambika Road,Pallikkunnu,Kannur-670004 | 12months | 25.10.2019 | 24.10.2020 | _ | Stair room roof slab concreting completed.Terrace column concreting completed.P.C.C work 60% completed.GF Masonry work started. | 60% | 58% | 52% | 0.6 | _ | Rema.P.K(GM) 9497186255 | Sri. Roy. P.S,RM, KSCC, Kannur,9447716468 | 1st&part bill sent on 25.08.2020
8 | KSCC |  |  | SCDD - Construction of Staff quarters (Type II) at Mannanthala in Thiruvananthapuram District | SCD002-02-05 | Thiruvananthapuram | - | - | 12 | - | - | - | Revised Estimate submitted to KIIFB for revised TS | [5 empty] | Rema.P.K(GM) 9497186255 | Geetha .A.V(RM)8547912529
9 | KSCC | SCD002-03 | Construction of Model Residential School At Kozhikod Chakkittappara | Construction of Model Residential School At Kozhikod Chakkittappara | _ | Kozhikode | [6 empty] | site already allotted is changed. So the estimate and design has to be changed. Preparation of drawing & estimate in progress. | [5 empty] | Rema.P.K(GM) 9497186255 | Ajith Kumar V V (RM), 8281882156
10 | KSCC | SCD002-04 | Construction of hostels at various locations (13 numbers) | STDD - Construction of 100 bedded Pre Matric Hostel for girls at Achankovil in Kollam District - Civil works | SCD002-04-01 | Kollam | 3.79 | Shri. S.Surendran Pillai | 12 | 05.07.18 | 04.07.19 | 05.07.2020 | Construction of Counterfort retaining wall in the back side is completed. Front side retaining wall completed and column footing 53 completed,short column concreting completed.lift shear wall comoleted. plinth beam completed. GF roof concreted on 27.8.2020.GF lintel,solid block work completed.Anti termite treatment and Floor PCC going on,FF roof reinforcement and shuttering works going on. | 75% | 48% |  | 0.64 | 0.17 | Rema.P.K(GM) 9497186255 | RAKESH C, RM 9447133269 | Second and part bill submitted. | october first week
11 | KSCC |  |  | STDD - Construction of Post Matric hostel for Boys at Kodalippara in Idukki District - Civil works | SCD002-04-02 | Idukki | 3.24 | Sri. E.M. Madhu, Eettical (H), Poonjar(S) P.O, Kottayam. | 12 months | 21.05.18 | 20.05.19 | 30.06.2020 | Work completed. | 100% | 100% | 100% | 2.26 | 69 | Smt.Rema P.K. General Manager in charge -EKM Ph-9497186255 | Mahin Aboobackar 9496335515 | CC IIIrd& Part bill on 14.08.2020 | Dec first week
12 | KSCC |  |  | Electrification of Post Metric Hostel for Boys at Kodalippara in Idukki District | SCD002-04-21 | Idukki | 11.89% | A.R.Sivasankaran Varappetty | 6 | 18.11.2019 | 17.05.2020 | 17.07.2020 | Complete | 100% | 100% | 100% | 0.12217 |  |  |  | 24.08.2020 | 24.10.2020
13 | KSCC |  |  | STDD - Construction of New hostel building for Boys at Nadukani in Idukki District - Civil works | SCD002-04-03 | Idukki | 2.8 | Sri.Tellus Stephene Kizhakkumthala House Mullapuzhalkkal P.O Vazhakkulam - 686670 | 12 months | 18.05.18 | 17.05.19 | 30.06.2020 | Work Completed. | 100% | 100% | 100% | 0.87 | 31 | Smt.Rema P.K. General Manager in charge -EKM Ph-9497186255 | Sunil.M.Roy 9400783789 | CC 1st& Part bill on 06.12.2019 | Nov Last week
14 | KSCC |  |  | Electrification of New hostel building for Boys at Nadukani in Idukki District | SCD002-04-16 | Idukki | 0.133 | A.R.Sivasankaran Varappetty | 6 | 10.10.2019 | 09.04.2020 | 09.10.2020 | Complete | 100% | 100% | 100% | [5 empty] | 30.09.2020
15 | KSCC |  |  | STDD - Construction of Pre Matric Hostel for 100 Boys at Kuttikkol in Kasargode District | SCD002-04-04 | Kasargode | 3.27 | Sri.C.L. Abdulla, C.L House, Kizhur, Chandragiri PO, Kasaragod 671 317 | 12months | 05.10.2018 | 04.10.2019 | 31.12.2020 | except interlock all work completed. | 100% | 99% | 99% | 3.87 | 78% | Smt.Rema P.K. General Manager -EKM Ph-9497186255 | Sri. Roy. P.S,RM, KSCC, Kannur,9447716468 | 3rd part bill under preparation | 15.11.2020
16 | KSCC |  |  | Electrification of Pre-Matric Hostel for 100 Boys at Kuttikkol in Kasargod District | SCD002-04-15 | Kasargode | 0.124 | Spands Electrcial Contractors | 6 | 05.10.2019 | 04.04.2020 | 04.10.2020 | 90% | 90% | 77% | [6 empty] | 30.09.2020
17 | KSCC |  |  | SCDD - Construction of 60 bedded Post Metric Hostel at Kozhinjampara in Palakkad District | SCD002-04-05 | Palakkad | 3.85 | Sri M Ahammedkutty Haji |  | 18/06/2018 | 17/06/2019 | #### | Work completed | 100% | 100% | 1 | 3.65 | 0.95 | Rema.P.K(GM) 9497186255 | K. Radhamany No-9605600308
18 | KSCC |  |  | Electrification of 60 bedded Post Metric Hostel at Kozhinjampara in Palakkad District | SCD002-04-17 | Palakkad | 0.131 | SunilKumar, Universal Electric Company | 3 | 18.09.2019 | 17.12.2019 | 17.11.2019 | Complete | 100% | 100% | 100% | 0.09232 | 0 |  |  | 21.12.2019 | 15.09.2020
19 | KSCC |  |  | SCDD - Construction of Hostel building for 100 plus two students at Vellachal in Kasaragod District - Civil works | SCD002-04-06 | Kasargode | 3.93 | Sri. Muhammed Harish. B.A, Najath (H), Baladkka, Kasaragod | 12months | 13.08.2018 | 12.08.2019 | 31.12.2020 | Structural work completed. Laterite Masonry completed. Plastering completed, electrification work in progress. plumbing 95% completed. painting 85% completed. joinary fittings 93%completed. water proofing completed.Tilework 95% completed.Handrail fixing completed.Yard levelling in progress.Septic Tank 70% completed.Truss work completed. | 100% | 88% | 82% | 3.25 | 37% | Rema.P.K(GM) 9497186255 | Sri. Roy. P.S,RM, KSCC, Kannur,9447716468 | 2 nd & part bill sent on 11.08.2020
20 | KSCC |  |  | Electrification of Hostel building for 100 plus two students at Vellachal in Kasargode District | SCD002-04-13 | Kasargode | 0.125 | Vinod Kumar, City Electricals | 6 | 16.09.2019 | 15.03.2020 | 15.10.2020 | 50% | 90% | 55% | [6 empty] | 30.09.2020
21 | KSCC |  |  | STDD - Construction of Post- Metric Hostel for Girls at Neriyamangalam in Ernakulam District - Civil works | SCD002-04-07 | Ernakulam | [6 empty] | Site handed over to the contractor on 20.02.2019. Setting out works were started on 26.04.2019. But Due to the objection from local people the work not started till date.As per the meeting held on 23.10.2019 in the presence of Hon’ble MLA Sri Antony John proposal for a new site location is suggested. The work could not be started as the site was changed by STDD. the arranged work was cancelled and the contract terminated.The construction in the new site require in principle approval from KIIFB along with approval for carrying out architectural drawing , soil investigation and structural design work in the new location. | [5 empty] | Rema.P.K(GM) 9497186255 | Rakesh C,(i/c)RMEKM,KSCC Ph No-9447133269
22 | KSCC |  |  | SCDD - Construction of Post - Metric Hostel for Boys at Aluva in Ernakulam District - Civil works | SCD002-04-08 | Ernakulam | 3.4724 | Civil - Shri Ashraf T A | 12 | 30.08.2018 | 29.08.2019 | 31.08.2020 | Interior Painting works completed and Exterior painting works in Ground floor in progress.Drainage work Completd and slab completed. | 95% | 90% | 94.74 | 1.57 | 45.21 | Rema.P.K(GM) 9497186255 | Rakesh C,(i/c)RMEKM,KSCC Ph No-9447133269 | CC 3rd and part bill dated 13.03.2020
23 | KSCC |  |  | Electrification of Post Metric Hostel for Boys at Aluva in Ernakulam District | SCD002-04-12 | Ernakulam | 0.117 | Biju Jose, Metro Contracting | 6 | 11.11.2019 | 10.5.2020 | 10.9.2020 | Complete | 100% | 100% | 100% | [5 empty] | 15.09.2020
24 | KSCC |  |  | STDD - Construction of Pre-Matric Hostel for 100 girls at Bedadukka in Kasaragod District - Civil works | SCD002-04-09 | Kasargode | 3.69 | Sri.C.L. Abdulla, C.L House, Kizhur, Chandragiri PO, Kasaragod 671 317 | 12months | 05.10.2018 | 04.10.2019 | 31.12.2020 | except interlock all work completed. | 100% | 99% | 99% | 4.45 | 69% | Rema.P.K(GM) 9497186255 | Sri. Roy. P.S,RM, KSCC, Kannur,9447716468 | 3rd & part bill under preparation | 20.11.2020
25 | KSCC |  |  | Electrification of Pre-Matric Hostel for 100 girls at Bedadukka in Kasargod District | SCD002-04-14 | Kasargode | 0.126 | Spands Electrcial Contractors | 6 | 15.09.2019 | 14.03.2020 | 14.10.2020 | 95% | 100% | 95% |  | 0.06922 | 0 |  |  | 21.12.2019 | 30.09.2020
26 | KSCC |  |  | SCDD -Construction of Post-Matric Hostel at Thana in Kannur District - Civil works | SCD002-04-10 | Kannur | 1.57 | Sri.Baby Joseph,Thachilettu House,Kuniyanpuzha.P.O,Kannur-670632 | 12months | 15.10.2019 | 14.10.2020 | _ | Ground floor slab concreting 50% completed.FF Column work completed.FF beam& Slab shuttering & steelwork completed..GF masonry in progress.. | 40% | 22% | 22% | 0.35 | _ | Rema.P.K(GM) 9497186255 | Sri. Roy. P.S,RM, KSCC, Kannur,9447716468 | 1st part bill under preparation | 10.11.2020
27 | KSCC |  |  | SCDD - Construction of Pre-Matric Hostel for 30 boys at Kathirur in Kannur District - Civil works | SCD002-04-11 | Kannur | 1.637 | Sri.M.Muhammed Kunji,Masthikund House,Muliyar P.O,Kasargod-671542 | 12months | 28.10.2019 | 27.10.2020 | _ | Structural work 90% completed.Inside plastering GF &FF 90% completed.Outside plastering started. | 60% | 52% | 52% | 0.84 | _ | Rema.P.K(GM) 9497186255 | Sri. Roy. P.S,RM, KSCC, Kannur,9447716468 | 1st part bill under preparation | 10.11.2020
28 | KSCC |  |  | STDD-Youth Hostel Peringamala,Palode | _ | Thiruvananthapuram | - | [5 empty] | Revised site location details recieved from STDD on 21.01.2020 only and AR drawing also has to be revised as the original plan cannot be accomadated in the new site. | [5 empty] | Rema.P.K(GM) 9497186255 | Geetha .A.V(RM)8547912529
29 | KSCC | SCD002-08 | Construction of Model Residential School at Thaliparamba, Kannur | SCDD -Construction of Model Residential School, Hostel, Staff Quarters and canteen block at Peringome in Thaliparamba in Kannur District - Civil works | SCD002-08-01 | Kannur | 12.62 | M/s. Hill Track Constructions (P) Ltd., Nadavayal PO, Panamaram, Wayanad - 670 721 | 18months | 17.09.2018 | 16.03.2020 | 31.12.2020 | School Building- Structural work completed. Plastering work completed. Tile laying completed. Al.fabrication work completed. Grills completed. Plumbing completed.Sanittary fixing completed. Painting 70%completed. handrail work completed. Hostel Building- Structural work completed. plastering work completed. Tile work 95% completed. Grill 90% completed. Plumbing completed. Handrail completed.Painting 70% completed .doors &windows shutter completed.Quarters Building- Laterite work for wall completed. Plastering work completed.plumbing 90% completed.door shutter 30%completed.window shutter fixing 20% completed.Painting 20% completed.Tiling work 30% completed.sanittary fittings GF completed.Canteen Building- Plastering work completed, PCC completed, Truss work completed.Tilework completed.door shutter fixing completed.Plumbing completed.False celiing completed.Painting 50%completed. | 94% | 86% | 75% | 10.9 | 58% | Rema.P.K(GM) 9497186255 | Sri. Roy. P.S,RM, KSCC, Kannur,9447716468 | 5th bill sent on 14.09.2020
30 | KSCC |  |  | Electrification of Model Residential School at Peringome in Kannur District | SCD002-08-02 | Kannur | 0.6196 | S.Suresh, Meco Electricals, Thamarasserry | 12 | 21.11.2019 | 20.11.2020 | 20.11.2020 | 75% | 100% | 75% | [6 empty] | 05.09.2020
31 | KSCC | SCD002-09 | STDD - Construction of Pre-Metric Hostel for 100 Boys at Pinavoorkudi in Ernakulam District | _ | _ | Ernakulam |  | The site for the proposed construction was changed thrice due to various reason. The project was approved as per Order No. SCD002-09-PA-02 Dated 20.09.2019 of Chief Executive Officer, KIIFB Estimate was prepared based on DSR 2016 by adding cost index @ 46.08%. Total estimate amount came to Rs.4,03,00,000/- for which FS obtained for Rs. 3,92,00,000/- Later cost index changed from 46.08% to 39.89% and GST 12% included,and also suggestions were put forward byKIIFB for making those changes in estimate. In this context estimate has been revised. After recalculating estimate amount comes to Rs.3,91,95,826.27. | [10 empty] | Rema.P.K(GM) 9497186255 | Rakesh C,(i/c)RMEKM,KSCC Ph No-9447133269
| KSCC | SCD002-16 | Construction of MRS at Thonnakkal, Thiruvananthapuram | Construction of Model Residential School at Thonnakkal in Thiruvananthapuram District | SCD002-16-01 | Thiruvananthapuram | - | [5 empty] | TS issued. Work tendered | [5 empty] | Rema.P.K(GM) 9497186255 | Geetha .A.V(RM)8547912529
32 | KSCC | SCD003-03 | Construction of Building for MRS Kuttichal | Construction of Model Residential School at Kuttichal in Thiruvananthapuram District | SCD003-03-01 | Thiruvananthapuram | - | [5 empty] | TS issued. Work to be tendered. | [5 empty] | Rema.P.K(GM) 9497186255 | Geetha .A.V(RM)8547912529
33 | KSCC | SCD003-04 | Construction of Model Residential School at Aralam, Kannur | STDD - Construction of Model Residential School, Hostels, canteen and Staff Quarters at Aralam in Kannur District - Civil works | SCD003-04-01 | Kannur | 15.88 | M/s. Hill Track Constructions (P) Ltd., Nadavayal PO, Panamaram, Wayanad - 670 721 | 18months | 02.11.2018 | 01.05.2020 | 01.11.2020 | Boundary compound wall 400 mtr Completed.School building- Walls and plastering work completed. Flooring completed except outer verandha. Toilet block- GF &FF Tile works completed .Doors and safety grills completed ,Septic tank completed,External &internal primer work completed. external plumbing works completed.Aluminium window shutters completed.Stair handrail work 80% completed.Ramp flooring completed.Septic tank&soakpit completed.sanittary fiitings 70% completed.Plinth protection completed.inside painting started. Staff Quarters-upto FF structural work completed .Second floor column work completed.Second floor lintel& sunshade concreting completed.SF slab shuttering work in progress..GF & FF masonry work upto lintel level 50% completed. Boys hostel-Walls completed ,Plastering completed. Flooring completed except stair .Stair handrail 75%completed. Doors and safety grills completed.GF&FF toilets- Tiles and Plumbing works completed, Primer work interior and exterior completed .Aluminium window shutters FFcompleted.External plumbing completed.Septic tank &soakpit completed Plinth protection work completed..Girls hostel- Plastering completed, Doors completed.window grill completed.Toilet blocks at GF&FF- tile and plumbing works completed.flooring 95% completed.External plumbing work completed.Stair handrail 75%completed. Primer 95% completed.Aluminium window shutters FF completed.Septic Tank &soakpit completed.Canteen-site clearing & general cutting completed. Excavation for foundation completed.Kitchen block plinth beam concreting completed.dining area column pedestal concrete in progress. | 100% | 85% | 75% | 13.5 | 48% | Rema.P.K(GM) 9497186255 | Sri. Roy. P.S,RM, KSCC, Kannur,9447716468 | 5th& part bill under preparation | 7.11.2020
34 | KSCC |  |  | Electrification of Model Residential School at Aralam in Kannur District | SCD003-04-02 | Kannur | 0.6837 | Sivaram, Jayanthi Electricals | 12 | 11.11.2019 | 10.11.2020 | 10.01.2020 | 70% | 87% | 85% | [6 empty] | 10.09.2020
35 | KSCC | SCD002-07 | Construction of Post Matric Hostel for ICSETS & PETC students at Mannanthala Thiruvananthapuram, Construction of Staff Quarters for Officers, Building construction of ITI Attippra & Ponnani at Malappuram | Construction of New Building for ITI at Ponnani in Malappuram District | SCD002-07-01 | Malappuram | Original proposal was as per NCVT norms of 2016.After receiving AS NCVT norms are changed.So revised estimate proposed for an amount of 218.7 Lakhs.RE not sanctioned so far. | [5 empty] | Original proposal was as per NCVT norms of 2016.After receiving AS NCVT norms are changed.So revised estimate proposed for an amount of 218.7 Lakhs.RE not sanctioned so far. | [5 empty] | Rema.P.K(GM) 9497186255
40